## Risk Categories
Project Name
RISK CATEGORIES & PxI MATRIX
Risk Identification Categories | Cat |  |  | Probability | Very High | 5 | 10 | 15 | 20 | 25 |  | RISK MATRIX - SPECIFIC
Highway (excl structures) | A |  |  | HARM % | [9 empty] | Low | Most Likely | High
Traffic | A1 |  |  | 90% | 5 | [5 empty] | 1 | Very low | 10% | 10000 | 35000 | 60000
Junctions | A2 |  |  | 70% | High | 4 | 8 | 12 | 16 | 20 | 2 | Low | 20% | 60000 | 90000 | 120000
Alignment | A3 |  |  |  | 4 | [5 empty] | 3 | Medium | 50% | 120000 | 240000 | 360000
X-sections, standards & safety | A4 |  |  | 50% | Medium | 3 | 6 | 9 | 12 | 15 | 4 | High | 70% | 360000 | 480000 | 600000
Design for Maintenance | A5 |  |  |  | 3 | [5 empty] | 5 | Very High | 90% | 600000 | 900000 | 1200000
Highway Construction risks | A6 |  |  | 20% | Low | 2 | 4 | 6 | 8 | 10
Geotechnics | B |  |  |  | 2
Design - Earthworks and ground conditions | B1 |  |  | 10% | Very Low | 1 | 2 | 3 | 4 | 5
Drainage design | B2 |  |  |  | 1 | [5 empty] | Cost | For construction between 10m to 14m
Pavement design | B3 |  |  |  | Impact | Very Low | Low | Medium | High | Very High | Time | Approx 18 months construction
Construction geotechnics risks | B4 |  |  |  |  | 1 | 2 | 3 | 4 | 5
Structures | C |  |  | = HIGH RISK | Cost | 10K/ 60K | 60K/120k | 120K/360K | 360K/600K | 600k/1,200k | Risk Matrix to be agreed by Project Services
Tunnels | C1 |  |  | = MEDIUM RISK | Time | <1 weeks | 1 week – | 4 weeks – | 7 weeks - 14 weeks | > 14 weeks
Major Overbridges/underbridges & Skew bridges | C2 | [5 empty] | 4 weeks | 7 weeks
Viaducts | C3 |  |  | = LOW RISK
Other | C4
Structures construction risks | C5 |  | Extremely low probablity risks i.e circa 1% can be identifed separately during the quantification stage if necessary.
Technology | D
E&M | D1 |  | Risk Assessment Guidance
High Tech | D2
IT Systems | D3 | 1 | Establish what is in the current estimate (if anything) - record background notes
Lighting & comms | D4 | 2 | The risk is the likelihood of it occurring over and above your normal project management/control activities
Technology risks during construction | D5 | 3 | Assess risk based on current knowledge/status - do not pre-judge whether risk mitigation will be achieved
Environment | E | 4 | Ask what is the likelihood /probablity of this risk accruing taking into account the above points
Environmental mitigation incl archeology | E1 | 5 | Use the 1-5 probability scale to make an assessment. Medium being as equally likely as not
Statutory bodies | E2 | 6 | Next assess the impact:
Environmental NGO's | E3 | 7 | Check for double counting/repeat risks and strike these out if necessary. Equally, check that the base estimate to ascertain if any allowance has already been made.
Environmental construction risks | E4 | 8 | If uncertain about the ratings, record the fact and note it for post workshop action.
3rd Parties | F | 9 | Once the cost and probability are completed under Risk Assessment, it is necessary to assign this risk to the appropriate Scheme Cost Heading and to the appropriate Phase of the project.
Statutory Undertakers | F1 | 10 | Make notes on how you arrived at the impact rating
Planning bodies & regulatory issues e.g LA's | F2 | 11 | Do not include in the cost impact the price of time delay - as this will begin double counting
Accommodation Workss/NGO's other | F3 | 12 | Use the time delay impact to rate the potential delay to the programme if the risk occurred again on the 1-5 scale
Protestors | F4 | 13 | Check for double counting/repeat risks and strike these out if necessary
3rd party construction risks | F5 | 14 | If you are uncertain about the ratings record the fact and note it for action post workshop
Land & Compensation | G | 15 | If time permits note the phase of the risk, any mitigation actions required and whether the employer will retain the risk or whether it will be transferred to the contractor
MSA's | G1
Land Acquistion | G2 |  | Cost Estimate Headings |  |  | Ref
Part 1 claims | G3 |  | Main Construction Contract |  |  | MCC
Land & compensation risks during construction | G4 |  | Main Contract Supervision |  |  | MCCS
Resources/Market | H |  | Archaeology |  |  | ARCH
Resource/Market | H1 |  | Advance Works & Other Contracts |  |  | ADVC
Other Resource/Market | H2 |  | Public Transport Connectivity/Asset Renewal |  |  | PTC
Pre-Construction Programme/Procurement | I |  | Land and Property |  |  | L&P
Public Inquiry & Objections | I1 |  | Planning and Design |  |  | P&D
Procurement Strategy change | I2
Other Pre-construction delay risks not already identified | I3 |  | Risk Timing - period when risk remains live:
Buildability & Construction Programme | J |  | Pre-construction
Buildability | J1 |  | Pre-CPO
Traffic Management | J2 |  | Construction
Phasing | J3
Interfaces with network and others | J4
Other Construction Delay Risks | J5
Finance | K |  | Strategic / Project
Error in Price basis risk - quants, methods,materials,equipment | K1 |  | Strategic |  | S
Inflation | K2 |  | Project |  | P
Tax | K3
Other-General | L
Legislation | L1
Political | L2 |  | Risk or Opportunity
Other Strategic | L3 |  | Risk |  | R
Traffic Modelling | L4 |  | Opportunity |  | O
Economical Appraisal | L5
Other | L6
Vehicle Restraint System | L7 |  | Timing - Applicable Phase
Phase 0 Scope and Pre-Appraisal
Phase 1 Concept and Feasibility
Phase 2 Options Selection
Phase 3 Design and Environmental Evaluation
Phase 4 Statutory Processes
Phase 5 Enabling and Procurement
Phase 6 Construction
Phase 7 Close out and Review
Risk Owner
Consultant
LA
RDO
TII
Other

## Risk Register
Project Name:
Risk Register Ref
Revision
Date
| RISK IDENTIFICATION | [8 empty] | RISK ASSESSMENT - PRE MIT | [6 empty] | RISK MANAGEMENT |  | RISK ASSESSMENT - POST MIT | [5 empty] | RISK QUANTIFICATION | [5 empty] | APPROX QUANTIFICATION OUTPUT (This is an initial quantification requiring post workshop review and further risk analysis)
Risk ID | Risks/Opportunities Title | Short List Option | Risk/Opportunity Description (cause event effect) | Category | Risk Owner | Cost Estimate Headings | Risk Timing - period when risk remains live: | Strategic / Project | Risk or Opportunity | Pre-mitigation Probability (P) | Pre-mitigation Cost/ Impact (C) | Pre-mitigation Time/ Impact (T) | Pre-mitigation Cost Rank (PxC) | Pre-mitigation Time Rank (PxT) | Comments/ Basis | Timing - Applicable Phase | Mitigation/Enhancement Measures | Mitigation Owner | Post-mitigation Probability (P) | Post-mitigation Cost/ Impact (C) | Post-mitigation Time/ Impact (T) | Post-mitigation Cost Rank (PxC) | Post-mitigation Rank (PxT) | Comments/ Basis | Prob | Min (€) | Most Likely (€) | Max (€) | Correlation | COMMENTS | P x Min (€) | P x Most Likely (€) (P50) | P x Max (€) (P80)
Highway (excl structures)
H1 | Example 1 | Route 1 Option | new risk | K1 | Consultant | MCC | Construction | P | R | 2 | 2 | 5 | 4 | 10 |  | Phase 6 Construction |  |  | 1 | 2 | 4 | 2 | 4 |  | 0.2 | 60000 | 90000 | 120000 |  |  | 12000 | 18000 | 24000
H2 | [9 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
H3 | [9 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Geotechnics
GEO1 | [9 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
GEO2 | [9 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Structures
S1 | [9 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
S2 | [18 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Technology
T1 | [9 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Environment
E1 | [9 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
3rd Parties
3P1 | [9 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Land & Compensation
LC1 | [9 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Resources/Market
RM1 | [9 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Pre-Construction Programme/Procurement
PC1 | [9 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Buildability & Construction Programme
BC1 | [9 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Finance
F1 | [9 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Other-General
G1 | [9 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Note on A7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Risk ID is unique for the risk and does not change through the life time of the project
Note on C7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For Phase 2 Route Selection
Note on F7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Risk Owner should be TII, LAs, Consultant or others