## Majors TSB Blank
SCHEME NAME | [6 empty] | TII Ref.
Road Authority | [6 empty] | Project Status |  |  |  |  | Region
Mainline Scheme Length |  | Cross Section |  |  |  | Current Date |  |  |  |  | NTT Date
Grade Separated Junctions |  | No. of Bridges |  |  |  | Start Year |  |  |  |  | Completion Year
Total Land Acquired (ha) | [5 empty] | Terrain |  |  |  | Ground Conditions
Budget Forecast Type: | Target Cost 1 / TSB (Prior to submission to ABP)
Base Cost Expenditure Heading |  | Base Cost (TSB Risk) | Current Risk Allocation to TC | Risk | % of Constr | Un-inflated Target Cost | Un-Inflated Target Cost Profile
|  |  |  | Analysis | Target Cost |  | Pre 2025 | 2025 | 2026 |  | 2027 | 2028 | 2029 | Post 2030
Main Contract Construction (incl VAT) |  |  |  | #DIV/0! |  | 0 | [7 empty] | 0
Employer Risks on Construction |  |  |  | #DIV/0! | 1
Main Contract Supervision | [5 empty] | 0 | [7 empty] | 0
Employer Risks on Supervision |  |  |  | #DIV/0! | #DIV/0!
Archaeology | [5 empty] | 0 | [7 empty] | 0
Pre-construction Archaeological Risks |  |  |  | #DIV/0! | #DIV/0!
Advance Works & Other Contracts | [5 empty] | 0 | [7 empty] | 0
Employer Risks |  |  |  | #DIV/0! | #DIV/0!
Public Transport Connectivity/Asset Renewal |  |  |  |  | #DIV/0! | 0 | [7 empty] | 0
Public Transport Connectivity/Asset Renewal Risks
Land & Property |  |  |  | #DIV/0! |  | 0 | [7 empty] | 0
Land Issues Risks |  |  |  | #DIV/0!
Planning & Design (incl GI & Topo) |  |  |  |  | #DIV/0! | 0 | [7 empty] | 0
Employer Risks on Planning & Design |  |  |  | #DIV/0!
Subtotal (Excl Inflation) |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[7 empty] | Inflation Item | [5 empty] | Inflation Level | % Inflation Allocated to TC
[7 empty] | Construction inflation 2019-2022 | [5 empty] | 4% | 100%
[7 empty] | Construction inflation 2023-2028 | [5 empty] | 3% | 100%
[7 empty] | Land & Property- Pre-Notice to Treat 2019-2022 | [5 empty] | 4% | 100%
[7 empty] | Land & Property- Pre-Notice to Treat 2023-2028 | [5 empty] | 3% | 100%
[7 empty] | Land & Property Post Notice to Treat 2019-2022 | [5 empty] | 4% | 100%
[7 empty] | Land & Property Post Notice to Treat 2023-2028 | [5 empty] | 3% | 100%
[7 empty] | Other Expenditure Heads 2019-2022 | [5 empty] | 4% | 100%
[7 empty] | Other Expenditure Heads 2023-2028 | [5 empty] | 3% | 100%
[7 empty] | Inflation Adjustment Factor | [6 empty] | 60%
[7 empty] | Programme Risk | [5 empty] | 5% | 0
Target Cost With Inflation |  | Un-inflated Target Cost | Inflation on Target Cost |  |  | Target Cost Adjusted for Inflation | Target Cost With Inflation Profile
[7 empty] | Pre 2025 | 2025 | 2026 |  | 2027 | 2028 | 2029 | Post 2030
Main Contract Construction |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Main Contract Supervision |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Archaeology All Phases |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Advance Works |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Walking/Cycling/Assett Renewal |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Land & Property |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Planning & Design (incl GI & Topo) |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Target Cost Totals |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
TARGET COST |  |  | TARGET COST / KM |  |  |  | #DIV/0! |  |  |  |  | 0
Base Cost | [11 empty] | 0 |  |  | Notes for TSB1 & TSB2: (Template set up for TSB3)
Total Inflation | [11 empty] | #DIV/0! |  |  | 1. TSB1 RCF, change the formula in cell C72 from 1.075 to 1.10
Programme Risk | [5 empty] | 5% | [5 empty] | #DIV/0! |  |  | 2. Change the text from (1.075) to (1.10) in cell E72
TOTAL SCHEME BUDGET | [11 empty] | #DIV/0! |  |  | 3. For TSB1, the uplift value changes from 1.19 to 1.32 (row 74)
Active Travel (Walking and Cycle) Costs |  |  | #DIV/0! |  |  |  | #DIV/0! | of the Scheme Budget (Contingency & Programme Risk | [6 empty] | 4. Row 75 formula needs amending from 1.19 to 1.32
RCF Total Scheme Budget
Target Cost-A (Un-Inflated) | 0 | (Base cost plus P50 Risk)
Target Cost-B (Un-Inflated) | 0 | (Base cost plus RCF Risk (1.075) | [9 empty] | RCF Inflation on TC |  | #DIV/0!
Apply Expert Judgement to Target Costs A and B. | [11 empty] | RCF Target Cost |  | #DIV/0!
If using RCF Target cost (B) apply the P80 value (1.19) to the Base Cost (less risk) to come up with a new base cost. | [11 empty] | RCF Target Cost/KM |  | #DIV/0!
New RCF Base Cost | [11 empty] | 0
RCF Total Inflation | [11 empty] | #DIV/0!
RCF Total Scheme Budget | [11 empty] | #DIV/0!
Following Expert Judgement the TSB for the scheme is __________
Note: Refer to the 'Signoff Matrix' tab for details of approval signitures required for each Budget Forecast Type.
Please delete signitory if they are not required for this particular budget
|  | Multiplier 2023-2028 | Multiplier |  |  | Pre 2025 | 2025 | 2026 |  | 2027 | 2028 | 2029 | Post 2030
| Construction | 1.0025 | 1.0033 |  |  |  |  | 0.03 |  | 0.0609 | 0.092727 | 0.12551 | 0.15927
|  |  | 60% |  |  |  |  | 60% |  | 60% | 60% | 60% | 60%
| Supervision | 1.0025 | 1.0033 |  |  |  |  | 0.03 |  | 0.0609 | 0.092727 | 0.12551 | 0.15927
|  |  | 60% |  |  |  |  | 60% |  | 60% | 60% | 60% | 60%
| Archaeology | 1.0025 | 1.0033 |  |  |  |  | 0.03 |  | 0.0609 | 0.092727 | 0.12551 | 0.15927
|  |  | 60% |  |  |  |  | 60% |  | 60% | 60% | 60% | 60%
Inflation Factors % | Advance works | 1.0025 | 1.0033 |  |  |  |  | 0.03 |  | 0.0609 | 0.092727 | 0.12551 | 0.15927
|  |  | 60% |  |  |  |  | 60% |  | 60% | 60% | 60% | 60%
| Walking/Cycling/Assett Renewal | 1.0025 | 1.0033 |  |  |  |  | 0.03 |  | 0.0609 | 0.092727 | 0.12551 | 0.15927
|  |  | 60% |  |  |  |  | 60% |  | 60% | 60% | 60% | 60%
| Land & Property | 1.0025 | 1.0033 |  |  |  |  | 0.03 |  | 0.0609 | 0.092727 | 0.12551 | 0.15927
|  |  | 60% |  |  |  |  | 60% |  | 60% | 60% | 60% | 60%
| Planning & Design | 1.0025 | 1.0033 |  |  |  |  | 0.03 |  | 0.0609 | 0.092727 | 0.12551 | 0.15927
|  |  | 60% |  |  |  |  | 60% |  | 60% | 60% | 60% | 60%
[6 empty] | Pre 2025 | 2025 | 2026 |  | 2027 | 2028 | 2029 | Post 2030
| Construction |  |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| Supervision |  |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| Archaeology |  |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Full Inflation | Advance works |  |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| Walking/Cycling/Assett Renewal |  |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| Land & Property |  |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| Planning & Design |  |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
[6 empty] | Pre 2025 | 2025 | 2026 |  | 2027 | 2028 | 2029 | Post 2030
| Construction |  |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| Supervision |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Archaeology |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Allocated Inflation | Advance works |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Walking/Cycling/Assett Renewal |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Land & Property |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planning & Design |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Intermediate Forecast (Pre-Target Cost 1)
Target Cost 1 / TSB (Prior to submission to ABP)
Intermediate Forecast (Pre-Target Cost 2)
Target Cost 2 / TSB (Prior to commencing land acquisition)
Intermediate Forecast (Pre-Updated Target Cost 2)
Updated Target Cost 2 / TSB (Prior to going to Tender)
Intermediate Forecast (Pre-Target Cost 3)
Target Cost 3 / TSB (Prior to awarding Main Contract)
Final Outturn Cost
FALSE | do not change cell
Engineering Inspector:_____________________________ Date:____________
Regional Manager:________________________________ Date:____________
Project Services:__________________________________ Date:____________
Head of Roads Capital Programme:_________________________ Date:_____________
Director of Capital Programme:____________________________ Date:_____________
Chief Executive:_________________________________________ Date:_____________

## Active Travel Cost Breakdown
TII Level 3 Active Travel Costs
1 | Series | Description |  | Level 3 Estimate | Active Travel Totals (€)
| Series 100 | Preliminaries
| Series 200 | Site Clearance
| Series 300 | Fencing and Environmental Noise Barriers
| Series 400 | Road Restraint Systems (Vehicles and Pedestrian)
| Series 500 | Drainage and Service Ducts
| Series 600 | Earthworks
| Series 700 | Pavements
| Series 1100 | Kerbs, Footways and Paved Areas
| Series 1200 | Traffic Signs and Road Markings
| Series 1300 | Road Lighting Columns and Brackets
| Series 1400 | Electrical Work for Road Lighting and Traffic Signs
| Series 1500 | Motorway Communications
| Series 1600 - 2300 | Structures
| Series 2500 | Special Structures
| Series 2700 | Watermains Utilities and Accommodation Works
| - | Landscaping
| - | Other Costs
| - | Other Costs
| Total Base Cost for Main Construction Contract (Excluding VAT) |  |  | 0 | 0
| Add VAT at |  | 13.5% | 0 | 0
| Total MCC Base Cost plus VAT |  |  | 0 | 0
Contingency
| Base Cost Total |  |  |  | 0
| Pro Rata Percentage of Main Construction Costs Contingency |  |  | #DIV/0! | #DIV/0!
| Total MCC Base Cost plus Project Specific Risk Contingency |  |  |  | #DIV/0!
2 | Main Contract Supervision (Active Travel)
| Provision based on percentage of Active Travel MCC total Cost |  |  | 8% | 0
| Pro Rata contingency for Main Contract Supervision (Active Travel) Costs |  |  | #DIV/0! | #DIV/0!
| Total Active Travel Main Contract Supervision Costs plus Contingency |  |  |  | #DIV/0!
3 | Archaeology
| Provision based on percentage of Main Construction Contract Base Cost |  |  | 7.5% | 0
| Pro Rata contingency for Archaeology (Active Travel) Costs |  |  | #DIV/0! | #DIV/0!
| Total Active Travel Archaeology Costs plus Contingency |  |  |  | #DIV/0!
4 | Advance Works and Other Contracts
| Provision based on percentage of Main Construction Contract Base Cost |  |  | 5% | 0
| Pro Rata contingency for Advance Works (Active Travel) Costs |  |  | #DIV/0! | #DIV/0!
| Total Active Travel Advance Works Costs plus Contingency |  |  |  | #DIV/0!
5 | Public Transport Connectivity/Asset Renewal
| Provision based on percentage of Main Construction Contract Base Cost |  |  | 7.5% | 0
| Pro Rata contingency for Advance Works (Active Travel) Costs |  |  | #DIV/0! | #DIV/0!
| Total Actice Travel Public Transport Connectivity/Asset Renewal Costs plus Contingency |  |  |  | #DIV/0!
6 | Land and Property
| LA to input approx percentage of overall land and property costs |  |  | 7.5% | 0
| Pro Rata contingency for Land and Property (Active Travel) Costs |  |  | #DIV/0! | #DIV/0!
| Total Active Travel Land and Property Costs plus Contingency |  |  |  | #DIV/0!
7 | Planning and Design
| Provision based on percentage of Main Construction Contract Base Cost |  |  | 8% | 0
| Pro Rata contingency for Planning and Design (Active Travel) Costs |  |  | #DIV/0! | #DIV/0!
| Total Active Travel Planning and Design Costs plus Contingency |  |  |  | #DIV/0!
LEVEL 3 ESTIMATE OF CYCLE COSTS INCLUSIVE OF VAT |  |  |  |  | #DIV/0!
| Base Cost plus contingency Total |  |  |  | #DIV/0!
| Inflation (Approx figure based on MCC) |  |  | #DIV/0! | #DIV/0!
| Programme Risk (5%) |  |  | 5% | #DIV/0!
TOTAL LEVEL 3 ESTIMATE OF ACTIVE TRAVEL COSTS INCLUSIVE OF VAT |  |  |  |  | #DIV/0!

## Expert Judgement Record
TII Reference Class Forecast
Expert Judgement Record
Project Name & PRS
Project Phase |  | Date of Workshop
Project Cost Forecast Data |  | Base Cost | € | 0
|  | Total QCRA Uplift | € | 0
|  | Total Ref Class Uplift | € | 0
Expert Judgement Team (Chair TII Senior Engineering Inspector)
Name | Reason for being on Expert Judgement Team
Application of Expert Judgement
Does the TII Reference Class for National Road Projects apply to this project?
If not, please provide reasons why not.
Does the project include particular circumstances such that the team judge that the project
project would be LESS risky than a typical TII National Roads project?
Please provide details.
Does the project include particular circumstances such that the team judge that the project
would be MORE risky than a typical TII National Roads project?
Please provide details.
On balance, which risk uplift figure (QCRA or Ref Class) is judged by the team to be appropriate
for this project cost forecast?
Please provide reasons for the choice of risk uplift figure
On behalf of the above referenced Expert Judgement Team, I confirm that the QCRA / Ref Class
(delete as appropriate) is the risk uplift figure to be applied to this project cost forecast.
Signed
Senior Engineering Inspector

## Signoff Matrix
Sign off required
Budget Forecast Type | Project Services | Engineering Inspector | Regional Manager | Head of Roads Capital | Director of Capital Programme | Chief Executive Officer
Intermediate Forecast (Pre-Target Cost 1) | ü | ü | ü | ü
Target Cost 1 / TSB (Prior to submission to ABP) | ü | ü | ü | ü | ü | ü
Intermediate Forecast (Pre-Target Cost 2) | ü | ü | ü | ü
Target Cost 2 / TSB (Prior to commencing land acquisition) | ü | ü | ü | ü | ü
Intermediate Forecast (Pre-Updated Target Cost 2) | ü | ü | ü | ü
Updated Target Cost 2 / TSB (Prior to going to Tender) | ü | ü | ü | ü | ü
Intermediate Forecast (Pre-Target Cost 3) | ü | ü | ü | ü
Target Cost 3 / TSB (Prior to awarding Main Contract) | ü | ü | ü | ü | ü | ü