## Appendix A1a_Lvl 1 FWC
FEASIBILITY WORKING COST
Inflation Factor Non Land Costs |  | 0.95 | Land | 0.95
Project Name
Road Authority
TII Ref.
Phase
X-Sec
Possible Mid-Construction Date |  |  |  | 0
Current Year |  |  |  | 0
Inflation-Construction |  |  |  | 3%
Inflation Land & Property |  |  |  | 3%
% Prog. Risk |  |  |  | 5%
Project Preliminary Scope
Mainline Length
Grade Separated Junctions
No. of Bridges (Ordinary)
No.Viaducts / Signature Structures
Active Travel Costs
All Costs in € Millions |  | Basic Cost (Incl VAT) |  | Project Specific Contingency | Total Project Cost (Excl Inflation & Programme Risk)
Main Contract Construction |  | 0 |  | 0 | 0
Main Contract Supervision |  | 0 |  | 0 | 0
Archaeology |  | 0 |  | 0 | 0
Advance Works and Other Contracts |  | 0 |  | 0 | 0
Public Transport Connectivity/Asset Renewal |  | 0 |  | 0 | 0
Land & Property |  | 0 |  | 0 | 0
Planning & Design |  | 0 |  | 0 | 0
Subtotal (from above) |  | 0 |  | 0 | 0
|  | Total Inflation Allowance |  |  | 0
|  | TII Programme Risk |  |  | 0
Feasibility Working Cost |  |  |  |  | 0
Notes (Major Assumptions / Risks / Exclusions) | Mid construction date is provisional
Project Services_________________________ |  | Senior Engineering Inspector___________________________
Regional Manager________________________ |  | Head of Roads Capital Programme ______________________

## Appendix A6 TC, TSB (Minors) (hidden)
ROUTE No. | [5 empty] | Date
SCHEME NAME | [5 empty] | PRS No
Road Authority | [6 empty] | Region?
Tick Appropriate Box
Estimate Only (sheet not signed) |  | Budget at Appraisal (TC1) |  |  | Budget prior to Tender Issue (TC2) |  | Budget at Tender Award (TC3) |  | Outturn Costs
Scheme Description
Scheme Programme, Status and Appraisal (when available)
Programme |  | Stage /Activity |  |  |  | Start [mm/yyyy] |  |  | Completion [mm/yyyy]
Design
EIS / NIS
CPO
Tender
Construction
Scheme Status |  | Land Acquisition
Planning Status
Appraisal |  | Status | [6 empty] | BCR
Approvals Granted |  | Undertake Detailed Design/Appraisal
Proceed to CPO/Purchase Land
Award Construction Tender
0
Base Cost Expenditure Heading |  | Base Cost (incl VAT) | Contingency | Contingency % | Budget € | Yearly Profiles (Euro)
[6 empty] | Pre 2018 | 2018 | 2019 | 2020 | Post 2020
Check Totals
Main Contract Construction |  |  |  | #DIV/0! | 0 | [11 empty] | Month | Archaeology | 0
Main Contract Supervision |  |  |  | #DIV/0! | 0 | [6 empty] | Planning & Design (incl GI & Topo) |  |  |  |  | Dec'12 | 11212 | 0
Archaeology |  |  |  | #DIV/0! | 0 | [6 empty] | Year | MNRPO | Jacobs | Check Sums |  | Jan'13 | 4360 | 0
Advance Works & Other Contracts |  |  |  | #DIV/0! | 0 | [6 empty] | 2011 | 162205 | 109181 | 271386 |  | Feb'13 | 6794 | 0
Residual network |  |  |  | #DIV/0! | 0 | [6 empty] | 2012 | 212723 | 193017 | 405740 |  | Mar'13 | 3089 | 0
Land & Property |  |  |  | #DIV/0! | 0 | [6 empty] | 2013 | 42000 | 230800 | 272800 |  | Apr'13 | 12 | 0
Planning & Design (incl GI & Topo) |  |  |  | #DIV/0! | 0 | [13 empty] | 0
TOTAL |  | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2015 | 42000 | 12433 | 54433 | Close-Out | June'13 | 8991 | 0
Programme Risk | [7 empty] | 0 |  |  |  | Total | 458928 | 545431 | 1004359 |  | Total | 34458
SCHEME BUDGET | [7 empty] | 0
SCHEME NAME | 0 | [7 empty] | PRS No | 0
Top Risks Considered under Main Contract Construction
|  | Risk # |  |  |  | Risk Description |  |  |  | Overall Impact
1
(and potential impact) |  | 2
3
4
5
6
7
8
9
10
|  | 11 | [7 empty] | 0
12
Total
Engineering Inspector:_________________________ Date:__________
Regional Manager:____________________________ Date:__________
Head of Roads Capital Programme:_______________________ Date:__________
Project Services:______________________________ Date:__________
Director of Capital Programme:__________________________ Date:__________
Chief Executive:_______________________ Date:___________
Note on P42: Richard Glancy: Jacob's MFC Fee = €602,781. Change Orders Estimate €20,000 TOTAL = €622,781.00
Note on V42: Richard Glancy: Expenditure 2013 Year to-date None anticipated for the remainder of the year.