.

Appendix L - Exchange Information Requirements (EIR) Template

June 2026

Contents

1.	Guidance on using this Template	1

2.	Document Scope and Purpose	2

2.1	Standards Relationship	2

3.	Project Information Standards (PIS)	4

3.1	Key Project Information	4

3.2	Organisation Structure and Commercial Relationships of the Project Team	4

3.3	Project directory	5

3.4	IM Strategic Purpose	5

3.5	Applicable Standards	5

3.6	Appointing Party Key Programme Decisions Points	5

3.7	Information Container Standards	6

3.8	Federation Strategy	6

3.9	Information Exchange Formats	6

3.10	Information Exchange Process	7

3.11	Modelling and Drawing Standards & Practices	9

3.12	CDE and Collaboration	9

3.13	Level of Information Need (LOIN)	10

3.14	Tender Response Requirements	11

3.15	Geospatial Information Systems (GIS) Implementation	12

3.16	4D and Digital Rehearsals	12

3.17	5D Process	12

3.18	Carbon Management	13

3.19	Health and Safety Management	13

3.20	Training and Competence	15

4.	Production and Exchange of Information	16

4.1	Design Assurance, Coordination Process and Clash Detection	16

4.2	Production, Review, Approval and Authorisation of Information.	16

5.	Information Assignment Matrix	17

6.	Information Security	20

7.	Cyber Security	21

8.	Project Reference Information	22

Appendix A - Acronyms and Abbreviations	23

# Guidance on using this Template

This Exchange Information Requirements (EIR) template should be used and completed by the relevant Appointing Party and issued as part of the Invitation to Tender (ITT) documentation.

The template is provided to support a consistent structure for defining information management requirements across projects. However, it is not intended to serve as a standardised document applicable to all projects, as project scale, complexity, procurement routes and delivery arrangements may vary significantly.

The Project Manager and Information Manager should review and adapt the contents of this template to ensure it is appropriate for the specific project scope, organisational structure, contractual arrangements and information management requirements, in accordance with the principles set out in the ISO 19650 series.

Any sections marked in Blue or [Insert Here] are for the Appointing Party to input or complete.

Any sections in Green are guidance for completing the template – delete prior to submission.

Please remove the highlighting prior to completing the document and delete this guidance section.

Should an Appointing Party wish to supplement this template, please ensure that original structure is maintained:

New sections should be added after the last original section

New sub-sections should be added after the last original sub-section

New columns in a table should be added to the Right

New rows in a table should be added beneath

# Document Scope and Purpose

The purpose of the Exchange Information Requirements (EIR) is to outline Appointing Party information requirements for information across the full project lifecycle.

EIR are populated at the inception of the project, and therefore reflect the best-known information requirements, at the time of creation.

The EIR answers responses to each of the common questions on a project:

What is the scope of the project?

What are the expected project delivery milestones?

What information needs to be produced?

Who is the party that should be responsible for creating this information?

The TII information delivery requirements are included within the associated GE-BIM-00101 - BIM for Infrastructure Implementation Guidelines for National Roads.

## Standards Relationship

Figure 2.1 explains the main concepts and relationship between applicable standards defined in Section 1.3 of the GE-BIM-00101 – BIM for Infrastructure Implementation Guidelines for National Roads.

Figure 2.1 – Standards Relationship

[Insert Here]

If there are any further use cases and goals from the organisations or project, then please add below.

# Project Information Standards (PIS)

This document provides supplementary information and clarifications to be used in conjunction with the BIM for Infrastructure Implementation Guidelines for National Roads GE-BIM-00101.

## Key Project Information

Table 3.1 – Key project Information

| Term | Description |
| --- | --- |
| Project Name | [Insert Here] |
| Project Number | [Insert Here] |
| Appointing Party (client) | [Insert Here] |
| Appointing Party Information Manager | [Insert Here] |
| Lead appointed Party (LAP) | [Insert Here] |
| LAP Information Manager | [Insert Here] |
| Appointed Party(ies) | [Insert Here] |
| Description (Works) | [Insert Here] |
| Survey Grid | IRENET95 / Irish Transverse Mercator (ITM). |
| Form of Appointment | [Insert Here] |
| Project Stage Commencement | [Insert Here] |
| [Insert Here] | [Insert Here] |

## Organisation Structure and Commercial Relationships of the Project Team

The organisational structure is outlined in Table 3.2.

Provide information in Table 3.2 below and an organisational chart / diagram. The forms of contract (NEC option C for example) should be captured If these are unknown then TBC is acceptable.

Table 3.2 – Organisational Structure

| Organisation Name | Scheme Role (Lead Appointed Party / Third Party / Appointed Party) | Project Role | Form of Contract |
| --- | --- | --- | --- |
| [Insert Here] | [Insert Here] | [Insert Here] | [Insert Here] |
| [Insert Here] | [Insert Here] | [Insert Here] | [Insert Here] |

## Project directory

Appointing Party key contacts and functions are outlined in Table 3.3.

Provide information in Table 3.3 below of the Appointing Party key contacts and their functions Add additional rows for task teams and people.

Table 3.3 – Appointing Party Team

| Function | Task Team (Discipline) | Organisation | Name | Email Address |
| --- | --- | --- | --- | --- |
| Project Information Manager | Information Management | [Insert Here] | [Insert Here] | [Insert Here] |
| Project Manager | Project Management | [Insert Here] | [Insert Here] | [Insert Here] |
| [Insert Here] | [Insert Here] | [Insert Here] | [Insert Here] | [Insert Here] |

## IM Strategic Purpose

The Lead Appointed Party (LAP) shall support and comply with the Transport Infrastructure Ireland (TII) strategic information management objectives, as summarised in Section 2 of BIM for Infrastructure Statement of Intent and Roadmap.

Please add additional Appointing party IM/BIM Goals and outline which initiatives LAP are required to implement on the project.

[Insert Here]

## Applicable Standards

The Lead Appointed Party shall comply with the information management standards and guidance outlined in Section 1.3 of GE-BIM-00101 – BIM for Infrastructure Implementation Guidelines for National Roads.

These standards establish the framework for information management, information production and exchange, and the management of information throughout the project lifecycle.

Please add additional Appointing party Applicable Standards.

[Insert Here]

## Appointing Party Key Programme Decision Points

The overarching framework for project decision points and information delivery milestones (stage gates) shall align with the requirements set out in Section 4 of GE-BIM-00101 – BIM for Infrastructure Implementation Guidelines for National Roads and the Project Management Guidelines (PMG) PE-PMG-02041.

These documents define the governance structure, key review stages and associated information requirements that support project decision-making throughout the project lifecycle.

The Appointed Parties shall ensure that information deliverables, including models, documentation and associated data, are prepared and submitted in accordance with these defined stage gates to support the Appointing Party’s review and approval processes.

Information deliverables associated with these decision points shall be clearly defined within the BIM Execution Plan and the Master Information Delivery Plan (MIDP) in accordance with the ISO 19650-2.

Please refine further project specific decision points and delivery milestones, Lead Appointed Party needs to comply with.

[Insert Here]

## Information Container Standards

The overarching information container naming convention and associated requirements are defined in Section 6 of GE-BIM-00101 – BIM for Infrastructure Implementation Guidelines for National Roads.

All Appointed Parties shall ensure that information containers are named, structured and managed in accordance with these requirements when creating, issuing and sharing information within the Common Data Environment (CDE). This includes compliance with the defined naming convention, metadata requirements, container status codes and revision management processes.

Provide any additional requirements LAP need to comply with, including any project specific metadata requirements.

[Insert Here]

## Federation Strategy

A federation strategy defines how separate information sources such as models, drawings, and data are brought together into a coordinated environment while remaining independently managed. It applies to both 2D and 3D information, ensuring consistency across all project outputs.

Project information shall be appropriately segregated in an asset and system-based approach in accordance with the project functional breakdown.

The Lead Appointed Party (LAP) shall develop a federation strategy for the Project Information Model (PIM). The Post-appointment BIM execution plan shall detail how the models and data will be segregated into manageable files and contain a list of the expected models on the project and how they relate to the systems or assets on the project.

Provide any additional requirements related to Federation Strategy that the LAP need to comply with.

[Insert Here]

## Information Exchange Formats

The Lead Appointed Party and Appointed Parties shall ensure that information is exchanged in accordance with the specified formats in Table 3.4 when delivering models, documentation, datasets and other information containers through the Common Data Environment (CDE).

Further to the requirements and guidelines provided in Section 4.2 of GE-BIM-00101, the project-specific information exchange formats shall be defined to ensure consistency, interoperability, and alignment with the project’s information management strategy. Both native and open/exchange formats shall be selected from the list below, or alternative formats and information types may be specified where required, to support the effective exchange of information across all disciplines and project stages.

Table 3.4 – Information Exchange Formats

| Information Type | Native Formats | Exchange Format |
| --- | --- | --- |
| Information / 3D Models | dwg, dgn, rvt, 3DM | ifc STEP |
| Project Information (Federated) Models | nwd, i.dgn, 3DM |  |
| 2D Models | dwg, dgn | dxf, dwfx |
| Drawings | dwg, dgn | pdf |
| Documents | docx, doc | pdf, odt |
| Semi structured Data | xlsx, xls | csv, pdf, ods, xml, bcf, ags |
| Presentations | ppt, pptx | pdf, odp |
| Photogrammetry 3D Mesh Models | obj, 3sm, 3mx | fbx, glb |
| GIS Data | shp, shx, dbf, prj, tab, geoJSON | gdb, web URLs |
| Aerial and satellite imagery | jpeg, ecw, geotiff, jpeg 2000 | jpeg |
| Point Cloud | las, pts, ptx, pod, xyz, ptd | e57 |
| Virtual Environment (VE) Models | umap, uasset, unity | fbx, glb, gltf |
| Video Files | avi, mp4 |  |
| Alignment File | IfcAlignment 1.0, OFC, LandXML 1.2, OFC GML 3.3 or higher |  |
| Terrain Data | LandXML, MX Genio |  |

## Information Exchange Process

The baseline information exchange processes that the Lead Appointed Party (LAP) shall comply with are defined in Sections 4 and 5 of GE-BIM-00101 – BIM for Infrastructure Implementation Guidelines for National Roads.

Table 3.5 outlines the information exchange frequency and the acceptable formats that the Lead Appointed Party (LAP) shall comply with when delivering and exchanging information throughout the project lifecycle.

Please review the below and provide omissions/amendments in line with project phase, scope and programme.

Table 3.5 – Exchange Frequency and Acceptable Formats

| Information Type | Frequency | Information Exchange Type | Required Format(s) Refer to Table 3.4 – Exchange (EX) Native (NA) | Target Systems |
| --- | --- | --- | --- | --- |
| Documentation | As per contract stages and project programme; Required for end of each stage. | Stage Exchange | EX and NA (end of stage gate) | E-CDE |
| Federated Information Models | Monthly intervals at “S2” status code. At the end of each stage. | Progress Exchanges | EX (monthly) and NA (end of stage gate) | E-CDE |
| Single Discipline Models | At the end of each stage | Stage Exchanges | NA (end of stage gate) | E-CDE |
| Drawings | As per contract stages and project programme; Required for end of each stage. | Stage Exchanges | EX and NA required for end of stage gate | E-CDE |
| Topographical Point cloud | At end of construction phase | Stage Exchanges | EX | E-CDE |
| Geospatial Information (GIS Data) | At end of stage | Progress Exchanges | EX | E-CDE |
| 4D Data | As per contract stages and project programme; Required for end of each stage. | Progress Exchanges | EX | E-CDE |
| 5D Data | As per contract stages and project programme; Required for end of each stage. | Progress Exchanges | EX | E-CDE |
| H&S Data | As per contract stages and project programme; Required for end of each stage. | Progress Exchanges | EX | E-CDE |
| MIDP | Monthly | Progress Exchanges | EX | E-CDE |
| Carbon Data | Monthly | Progress Exchanges | Refer to Section 3.9 of this document. | E-CDE |
| Aerial Imagery | Monthly | Progress Exchanges | EX | E-CDE |

Provide any additional project specific requirements.

[Insert Here]

## Modelling and Drawing Standards & Practices

The modelling and CAD standards that the Lead Appointed Party (LAP) shall comply with are defined in GE-BIM-00102 – BIM for Infrastructure Modelling and CAD Standards.

The Lead Appointed Party and all Appointed Parties shall ensure that models, drawings and associated graphical information are produced in accordance with the requirements set out in this document, including modelling conventions, drawing production standards, coordinate systems, layering, classification and graphical representation.

These standards shall be applied to ensure consistency, interoperability and quality of graphical information across the project, supporting effective coordination, review and information exchange within the Common Data Environment (CDE).

Provide any additional project specific requirements related to CAD or Modelling requirements.

[Insert Here]

## CDE and Collaboration

The Lead Appointed Party (LAP) shall comply with the Common Data Environment (CDE) guidelines  and processes outlined in Section 7.2 of GE-BIM-00101 – BIM for Infrastructure Implementation Guidelines for National Roads.

This section shall define any project-specific requirements and clearly set out how the Lead Appointed Party (LAP) is to deliver information to the Appointing Party.

For projects with an estimated value below €10 million, including safety improvement schemes and maintenance works (e.g. pavement renewal), the responsibilities of the Appointing Party (Client) to mobilise and operate a Client-facing Common Data Environment (CDE), as outlined in Section 7.2 of GE-BIM-00101 – BIM for Infrastructure Implementation Guidelines for National Roads, are optional.

In such cases, a proportionate approach should be adopted. This may include the use of simpler document management systems in place of a Client-owned CDE, provided that information is managed in a controlled, secure, and accessible manner appropriate to the scale and complexity of the project.

Where this approach is adopted, this section shall clearly define, the document management system to be used by the Appointing Party for receiving project information.

[Insert Here]

## Level of Information Need (LOIN)

Lead Appointed Party shall comply with the guidelines of the LOIN frameworks summarised in section 8 of the GE-BIM-00101 - BIM for Infrastructure Implementation Guidelines for National Roads.

In addition to section 8, provide details in this specifying the level of information need (LOIN) guidance and standards in line with the specific project stage and scope.

Key questions to answer when determining the LOIN for the project are:

Why do you need the information? Understanding the purpose supports better process and transparency

When is the information needed? Is it a one-time request or a regular need?

Who will the information be shared with? Identifying the "Actors" ensures it reaches the correct parties?

What specific object, part, or assembly does the request relate to?

How should the information be provided (i.e. what is the required level of detail)

[Insert Here]

### Level of Geometrical Information

Level of Geometrical Information asset catalogue are summarised in section 8 of the GE-BIM-00101. Select the appropriate scope elements from the Level of Geometrical Information Appendix K GE-BIM-00101. Define as detailed as practical what is expected from the Lead Appointed Party. The selected Level of Geometrical Information shall be appropriate to support the project purposes and initiatives summarised in Section 3.4 of this document.

Over-specification of Level of Geometrical Information requirements may introduce unnecessary cost to the project. Therefore, Level of Geometrical Information should clearly reflect which project purpose it is for.

[Insert Here]

### Level of Alphanumerical Information

Alphanumerical level of information need. Define as detailed as practical what is expected from The Lead Appointed Party.

[Insert Here]

For the delivery of ATI Asset Repair and Renewal (ATARR) Schemes funded and overseen by TII Network Management (TII NM), or where applicable to the project scope:

The Lead Appointed Party shall comply with the alphanumerical information requirements set out in AM-PAV-06049 Pavement Asset Repair and Renewal – Scheme Approval Procedures.

### Level of Information for Documentation

The Lead Appointed Party shall refer to the condition of contract, the scope, TII publications and any other relevant industry standards for the appropriate descriptions of the contents, quantity, quality and granularity of documents to be supplied to the Appointing Party.

Level of the information need for all other deliverables not covered by section 3.13.1 and 3.13.2 of this EIR. These are typically defined by other relevant TII publications, hence reference to them is sufficient.

[Insert Here]

## Tender Response Requirements

The Information Management deliverables required as part of the tender submission are outlined in Section 5 of GE-BIM-00101 – BIM for Infrastructure Implementation Guidelines for National Roads.

The Lead Appointed Party (LAP) shall ensure that all required information management documentation and responses are prepared and submitted in accordance with these guidelines.

For projects valued below €10m, including safety projects and maintenance schemes (such as pavement renewal), the requirement to submit a pre-appointment BIM Execution Plan (BEP), Capability and Capacity Assessment, Mobilisation Plan, and Information Delivery Risk Assessment at the tender stage should be treated as optional. Where this approach is adopted, this section shall be amended/deleted accordingly.

If applicable provide any additional project specific tender response requirements. Where the appointing party has defined specific Key Performance Indicators (KPIs) or project outcomes such as achieving biodiversity net gain, reducing embodied carbon, enhancing social value, or meeting sustainability targets; these should be explicitly incorporated into the tender response requirements and associated evaluation criteria.

In such cases, tendering parties shall be required to demonstrate, within their tender submissions, how their proposed approach to BIM and IM will support the achievement of these KPIs. This may include, but is not limited to:

- Proposed methods for capturing, managing, and reporting relevant data through the Common Data Environment (CDE)

- The use of structured data to monitor progress against environmental and sustainability targets

- Integration of geospatial and ecological datasets to support biodiversity planning and evaluation

- Implementation of digital tools and workflows to simulate, assess, and optimise KPI delivery outcomes

- Proposed performance indicators or dashboards for measuring and communicating progress during the project lifecycle

The Appointing Party (Client) shall define in advance how responses to these KPI-related requirements will be evaluated and scored as part of the overall tender assessment. Evaluation criteria should consider the relevance, feasibility, and digital maturity of the proposed approach, as well as the competency of the delivery team to execute it effectively.

By embedding project-specific KPIs into the tender process, the appointing party ensures alignment between strategic project outcomes and the capabilities of the appointed delivery team from the outset.

[Insert Here]

## Geospatial Information Systems (GIS) Implementation

This is an optional section to include details on how GIS shall be implemented by LAP. Delete the section if not applicable or relevant to the scope of works.

Include:

- Roles

- Technology

- How GIS deliverables shall be generated and leveraged.

- GIS Use cases

- GIS Data naming

- GIS Metadata requirements

[Insert Here]

## 4D and Digital Rehearsals

This is an optional section to include details on how “4D – Digital rehearsals” should be implemented by LAP. Delete the section if not applicable or relevant to the scope of works. The requirement for 4D modelling should be specified at the discretion of the Appointing Party (Local Authority), considering the scale, complexity, and risk profile of the project. Over-specification of 4D requirements may introduce unnecessary cost to the project. Therefore, 4D digital rehearsals should only be required where they provide clear value in planning, coordination, or risk mitigation.

If the decision was made to include this section. Further guidelines are outlined in section 9.1 of the GE-BIM-00101 - BIM for Infrastructure Implementation Guidelines for National Roads.

[Insert Here]

## 5D Process

This section is optional and may be included to describe how 5D BIM (cost and quantity integration) will be implemented by LAP. The requirement for 5D BIM should be specified at the discretion of the Local Authority, considering the scale, complexity, and stage of the project. Where not considered necessary, this section should be removed.

Over-specification of 5D requirements may introduce unnecessary cost to the project. Therefore, 5D BIM should only be required where it provides clear value in cost planning, quantity verification, or financial control during project delivery.

If the decision was made to include this section. Further guidelines are outlined in section 9.2 of the GE-BIM-00101 - BIM for Infrastructure Implementation Guidelines for National Roads.

[Insert Here]

## Carbon Management

The carbon management requirements Lead Appointed Party shall comply with are outlined in Section 9.3 of the GE-BIM-00101 - BIM for Infrastructure Implementation Guidelines for National Roads.

Section to include requirements on how BIM dimension Carbon Management, shall be implemented by LAP. If Appointing Party would like to add any further requirements, in line with the project scope please list them below. As a minimum include use cases, outputs and technology.

[Insert Here]

## Health and Safety Management

Lead Appointed Party shall comply with the section 9.4 of the GE-BIM-00101 – BIM for Infrastructure Implementation Guidelines for National Roads.

Include any project specific requirements on how BIM shall be used by LAP for Health and safety management. Questions below will help you to clearly define H&S information requirements ensuring safer project execution and long-term H&S data usability:

- Existing Information: What H&S-related project information do you as a client already have or need at the project’s initiation?

- Monitoring & Management: What systems are in place to track and manage H&S information effectively?

- Common Data Environment (CDE): What H&S information must be specified for the CDE to enhance communication and risk awareness?

- Risk Studies & Reviews: What risk assessments and collaborative reviews are planned to eliminate or reduce hazards?

- Design Risk Objectives: What objectives should guide the design team in minimizing project risks?

- Collaboration in Design Risk Management: Has a design plan been requested to ensure coordination among disciplines?

- Model Integration: Design models which include H&S information for future use?

- Testing & Commissioning: What early arrangements will ensure the final build meets specifications and supports operational H&S?

- Health & Safety File: How shall H&S information be compiled and made available to end users?

- Lessons Learned: How insights from this project be captured and applied to improve future H&S practices?

[Insert Here]

### H&S Context

Information about the context shall be described so that any risks and incidents can be associated with appropriate context. The granularity of the context will depend on the objectives of the Appointing Party.

The H&S context summary is summarised in Table 3.6.

Table 3.6 - H&S Context Schema

| Property field | Specification | Explanation | Code |
| --- | --- | --- | --- |
| Identifier | Text | Unique context identifier Shall define or describe the “project/asset”. | [Insert Here] |
| Category | Enumeration | Classification of the asset | [Insert Here] |
| Description | Text | Detailed description and narrative of the asset | [Insert Here] |
| Associated product | Text or identifier | “Element or system”. Only systems that are exceptional given the overall context need to be recorded. | [Insert Here] |
| Associated activity | Text or identifier | Asset life cycle stage or work package. In line with PE-PMG-02041. | [Insert Here] |
| Associated location | Text or identifier | Spatial Zone Only zones that are exceptional given the overall context need to be recorded | [Insert Here] |
| Contextual location | Coordinates | Coordinate system-based location Optional. This can be cartesian, geo-spatial or alignment based | [Insert Here] |
| Context link | Text or link to main context | If additional context needs to be taken into consideration it needs to be specified here | [Insert Here] |
| Context linkage | Inverse links to sub-contexts | If additional sub-context needs to be taken into consideration it needs to be specified here Optional depending on implementation. | [Insert Here] |
| Risk linkage | Inverse linkage to risks | Optional depending on implementation. | [Insert Here] |
| Incident linkage | Inverse linkage to incidents | Optional depending on implementation. | [Insert Here] |
| History | Varies | Record of dates and actions including creation, updates Entries shall not be deleted | [Insert Here] |

## Training and Competence

### Competence

The Lead Appointed Party (LAP) shall undertake project-specific supply chain capability and capacity assessments and provide an overview and summary of the assessment outcomes.

The assessment can be carried out using the Capability and Capacity Assessment Template, provided in Appendix M of GE-BIM-00101 – BIM for Infrastructure Implementation Guidelines for National Roads.

In addition to the above, provide details on the project specific competence requirements.

[Insert Here]

### Training

The minimum information management requirements that the Lead Appointed Party (LAP) shall comply with are summarised in Section 10 of GE-BIM-00101 – BIM for Infrastructure Implementation Guidelines for National Roads.

For training, please include training requirements that shall be delivered as part of the works to the project staff. Outline in this section any training which will be provided by Appointing party to LAP and at what frequency.

[Insert Here]

# Production and Exchange of Information

## Design Assurance, Coordination Process and Clash Detection

The Lead Appointed Party (LAP) shall comply with the guidelines outlined in GE-BIM-00101 – BIM for Infrastructure Implementation Guidelines for National Roads.

Provide details on the co-ordination process for clash detection and issue management (if any), and approval processes for the design assurance.

[Insert Here]

## Production, Review, Approval and Authorisation of Information.

The Lead Appointed Party (LAP) shall comply with the information production methods and procedures guidelines outlined in GE-BIM-00101 – BIM for Infrastructure Implementation Guidelines for National Roads.

Provide any additional details on how procedures outlined in I.S. EN ISO 19650-1:2018 Section 12 shall be applied.

[Insert Here]

# Information Assignment Matrix

Complete the table below to define the allocation of information management responsibilities for the project. The Table 5.1 is pre-populated with typical responsibilities aligned with ISO 19650 information management processes. These should be reviewed and adjusted to reflect the project-specific roles, organisational structure and contractual responsibilities within the delivery team.

Table 5.1 - Responsibility Matrix (Source: ISO 19650-2 Annex A)

| Key R – Responsible for undertaking activity A – Accountable for activity completion C – Consulted during activity I – Informed following activity completion |  | Appointing party | Third party | Lead appointed party | Appointed party |
| --- | --- | --- | --- | --- | --- |
| ISO 19650-2 Task |  |  |  |  |  |
| 5.1, 5.2 Assessment, need and Invitation to Tender |  |  |  |  |  |
| 5.1.4 | Establish the project’s information standard | A/R | I | I | I |
| 5.1.7 | Establish the project's common data environment | A/R | I | I | I |
| 5.1.8 | Establish the project's information protocol | A/R | I | I | I |
| 5.2.4 | Compile invitation to tender information | A/R | I | I | I |
| 5.3 Tender Response |  |  |  |  |  |
| 5.3.1 | Nominate individuals to undertake the information management function | I | A/R | A/R | A/R |
| 5.3.2 | Establish the delivery team's (pre-appointment) Information Execution Plan | I | C | A/R | C |
| 5.3.3 | Assess each task team’s capability and capacity | I | C | A/R | C |
| 5.3.4 | Establish the delivery team's capability and capacity | I | C | A/R | C |
| 5.3.5 | Establish the delivery team’s mobilization plan | I | C | A/R | C |
| 5.3.6 | Establish the delivery team’s risk register | I | C | A/R | C |
| 5.3.7 | Compile the delivery team's tender response | I | C | A/R | C |
| 5.4 Appointment |  |  |  |  |  |
| 5.4.1 | Confirm the delivery team's BIM execution plan | I | C | A/R | C |
| 5.4.2 | Establish the delivery team’s detailed responsibility matrix | I | C | A/R | C |
| 5.4.3 | Establish the lead appointed party’s exchange information requirements | I | I | A/R | I |
| 5.4.4 | Establish the task information delivery plan(s) | I | C | A/R | C |
| 5.4.5 | Establish the master information delivery plan | I | I | A/R | I |
| 5.4.6 | Complete lead appointed party’s appointment documents | I | I | A/R | I |
| 5.4.7 | Complete appointed party’s appointment documents | I | A/R | I | A/R |
| 5.5 Mobilisation |  |  |  |  |  |
| 5.5.1 | Mobilize resources | C | C | A/R | C |
| 5.5.2 | Mobilize information technology | C | C | A/R | C |
| 5.5.3 | Test the project’s information production methods and procedures | C | C | A/R | C |
| 5.6 Collaborative Production of Information |  |  |  |  |  |
| 5.6.1 | Check availability of reference information and shared resources | C | C | A/R | C |
| 5.6.2 | Generate information | I | A/R | A/R | A/R |
| 5.6.3 | Undertake quality assurance check | I | A/R | A/R | A/R |
| 5.6.4 | Review information and approve for sharing | I | A/R | A/R | A/R |
| 5.6.5 | Information model review | I | I | A/R | I |
| 5.7 Information Model Delivery |  |  |  |  |  |
| 5.7.1 | Submit information model for lead appointed party authorisation | I | A/R | I | A/R |
| 5.7.2 | Review and authorize the information model | I | I | A/R | I |
| 5.7.3 | Submit information model for appointing party acceptance | I | I | A/R | I |
| 5.7.4 | Review and accept the information model | A/R | I | I | I |
| 5.8 Project Close-out |  |  |  |  |  |
| 5.8.1 | Archive the project information model | A/R | C | C | C |
| 5.8.2 | Capture lessons learned for future projects | A/R | A/R | A/R | A/R |
| ISO 19650-5 |  |  |  |  |  |
| 4.2 | Determine the range of security risks | C | I | A/R | I |
| 4.7 and 4.8 | Undertake the security triage process and record the outcome | C | C | A/R | C |
| 6 | Develop and maintain a security strategy (If required) | C | C | A/R | C |
| 7 | Develop and maintain a security management plan (If required) | C | C | A/R | C |

# Information Security

The Lead Appointed Party (LAP) shall comply with the information security requirements outlined in Section 12 of GE-BIM-00101 – BIM for Infrastructure Implementation Guidelines for National Roads.

Include details on what project specific security requirements LAP shall comply with. If Appointing party information security policies are not covered anywhere else, then please detail compliance in this section.

[Insert Here]

# Cyber Security

The Lead Appointed Party shall comply with cyber security requirements outlined in the GE-BIM-00101 – BIM for Infrastructure Implementation Guidelines for National Roads Section 12.

This section is optional. If there are other documents that cover Cyber Security that have been/will be submitted, then this section can be left blank.

If Appointing party cyber policies are not covered anywhere else, then please detail compliance in this section.

[Insert Here]

# Project Reference Information

This section can be used for the projects to reference internal templates, resource files etc for project team use. Suggestion is that it is contained in tables and hyperlinks provided:

Table 8.1 - Project Reference Information

| Document number | Document Title | Link |
| --- | --- | --- |
| [Insert Here] | [Insert Here] | [Insert Here] |

###### - Acronyms and Abbreviations

Delete if specific acronyms are not used.

| Acronym | Definition |
| --- | --- |
| 3D Exchange Models | Geometrical Models containing 3D representations of the scheme’s assets, divided as per an agreed breakdown structure. The main objective of 3D Exchange Models is to facilitate the exchange and sharing of geometrical asset information between project team members and other project’s stakeholders. They are normally supplied in open data formats and/or industry- wide proprietary formats to minimise interoperability issues and reduce risks associated with obsolescence. |
| AIM | Asset Information Model Set of structured and unstructured Information Containers relating to the operational phase of a project. |
| AIR | Asset Information Requirements This defines the information that is required, and the managerial and technical aspects of producing this information, for the operation of an asset to meet the OIR. |
| Alphanumerical Information Containers | Information Containers holding non-graphical content that can be expressed using characters, digits and symbols, or tokens such as mathematical symbols and punctuation marks, and are normally structured in a tabular/matrix format. These are mainly used to record relevant attributes/data associated with infrastructure assets. |
| AR | Augmented reality A technology that superimposes a computer-generated image on a user's view of the real world, thus providing a composite view. |
| ATARR | ATI Asset Repair and Renewal |
| BEP | BIM Execution Plan Plan that explains how the information management aspects of the Appointment will be carried out by the Delivery Team. NOTE 1: A pre-appointment BIM Execution Plan focuses on the delivery team's proposed approach to information management and their capability and capacity to manage information. NOTE 2: A post-appointment BIM Execution Plan is the contractual, document, produced after appointment that confirms exactly how the Delivery Team will implement information management to meet the Appointment requirements. NOTE 3: Specific terminology can be applied to contracts, for example the equivalent term for 'BIM execution plan' under NEC 4 terminology is the 'Information Execution Plan (IEP)'. |
| BIM | Building Information Modelling Use of a shared digital representation of a built asset to facilitate planning, design, construction and operation processes to form a reliable basis for decisions. |

| Acronym | Definition |
| --- | --- |
| BIP | BIM Implementation Plan Strategic roadmap for how an organisation or company may adopt and utilise Information Management within and across different project phases |
| CDE | Common Data Environment A combination of process workflows and technical solutions used to collect, manage and disseminate structured and unstructured information (information containers) for a project or asset. The CDE workflow defines the processes, and the CDE solutions are the technologies that enable those processes, with appropriate access, control, status/metadata and auditability. Used in combination with a digital storage solution, information is shared collaboratively in a logical and accessible way to help all key parties readily gain access to information, use consistent naming conventions, avoid duplication and retain ownership. |
| E-CDE | Appointing Party Common Data Environment A combination of process workflows, governance arrangements and technical solutions established and operated by the appointing party (client) to collect, manage and disseminate structured and unstructured information (information containers) across projects and asset portfolios. The E-CDE provides the client’s enterprise-level information management environment, defining how information delivered from project Common Data Environments (CDEs) is received, validated, stored and managed for organisational, operational and asset management purposes. The E-CDE workflows define the processes for information exchange between project teams and the appointing party, while the E-CDE technical solutions provide the technologies that enable these processes, including appropriate access control, metadata management, information status, security and auditability. Used in conjunction with enterprise digital storage and asset information systems, the E-CDE enables the appointing party to maintain a consistent, structured and accessible repository of project and asset information, supporting governance, lifecycle management, operational use and long-term information retention across the asset portfolio. |
| Clash Avoidance | Process of proactively preventing spatial coordination overlaps and interface issues associated with the Design, employing robust interdisciplinary collaboration techniques. This process is applied prior to Clash Detection. |
| Clash Detection | Process of identifying if elements of the Design are over overlapping both spatially and chronologically, and if so, where and how these interferences occur. Modern software offers tools to automate this process. |
| Contract | Is a legally binding agreement between two or more parties that creates enforceable rights and obligations. |
| CWMF | Capital Works Management Framework Is a structure that has been developed to deliver the Republic of Ireland Government’s objectives in relation to public sector construction procurement reform. |

| Acronym | Definition |
| --- | --- |
|  | It consists of a suite of best practice guidance, standard contracts and generic template documents that form the four pillars that support the Framework. |
| DBP | Digital Build Project Project led by Technological University Dublin (TU Dublin) to unite all construction and built environment stakeholders to drive integrated, interoperable digital data adoption across the industry to innovatively improve efficiency, productivity, and international competitiveness on a sustainable basis in Ireland. |
| EIR | Exchange Information Requirements A documented set of managerial, commercial and technical requirements for the production and exchange of project information. EIR defines the information to be delivered, the standards, methods and procedures to be applied by the delivery team and relevant project stage trigger milestones. |
| FIDIC | International Federation of Consulting Engineers An international standards organisation for construction technology and consulting engineering. The organisation is best known for the FIDIC suite of contract templates. |
| Geographical Information System (GIS) | Framework comprising computer-based tools and applications that provides the ability to capture and analyse spatial and geographic data. |
| Geometrical Models | Information Containers used to represent physical infrastructure assets, comprising information expressed using shape, size, dimension, and location. |
| H&S | Health and Safety |
| ICMS | International Cost Management Standard International standards for benchmarking, measuring and reporting construction project costs. |
| IFC | Industry Foundation Class Open data format. |
| IM | Information Management The function and associated activities used to define information requirements, plan and control information production, and manage the delivery and checking of information to meet the needs of a project or asset |
| IMI | Information Management Initiative Led by the Construction Leadership Council (CLC) the initiative aspires to become an industry-led and government-supported programme to progressively transform information management practices across the built and natural environment sector [1]. |
| Information Container | Named persistent set of information retrievable from within a file, system or application storage hierarchy. Information Containers can comprise directories, folders, files, layers and symbols. |
| Information Exchange | Information delivered to the Appointing party at a pre-defined milestone/point in the project, which satisfies the EIR. |
| Information Management Deliverables | Resources, documentation and content prepared to support the effective management of information in a project in accordance with the I.S. EN ISO 19650 series. |
| IT | Information technology Refers to the systems, infrastructure, and tools used to support the creation, management, exchange, and delivery of digital information throughout a built asset’s lifecycle. |
| JCT | The Joint Contracts Tribunal Standard forms of contract for construction. |
| LAP | Lead Appointed Party |
| Level of Geometrical Information | Description of graphical content for Geometrical Models. |
| Level of Alphanumerical Information | Description of non-graphical content for Geometrical Models and Alphanumerical Information Containers. |
| Level of Information for Documentation | Description of the content for project documentation such as drawings, text documents, schedules and photos. |
| MIDP | Master Information Delivery Plan A plan that incorporates all relevant Task Information Delivery Plans (TIDP) |
| Mobilisation Plan | Plan that details the approach, timescales and responsibilities for the configuration and deployment of the necessary infrastructure and resources associated with the production and delivery of the Project Information. |
| NPSA | National Protective Security Authority |
| OGP | Office of Government Procurement Plays a leading role in public procurement reform as part of the Department of Public Expenditure, Infrastructure, Public Service Reform and Digitalisation. |
| OIR | Organisational Information Requirements This specifies what information is required to achieve an organisations strategic objectives in relation to business operation, asset management, portfolio planning etc. The OIR may be developed from an ISO 55001 asset management system. |
| PIM | Project Information Model Composite information model created from separate Geometrical Models. It can embed, or be linked to, non-graphical data of modelled assets. Note: In the context of this document Federated Model and PIM has the same meaning. |

| Acronym | Definition |
| --- | --- |
| PIR | Project Information Requirements This specifies the information that is required related to a specific project consisting of the relevant information from the OIRs and AIRs. |
| Project Information | Information produced and managed during the project delivery phase (including geometrical information, alphanumerical information and documentation) and controlled through the CDE. |
| PIS | Project Information Standard |
| PWCF | Public Works Contract Form(s) as published by the OGP |
| RIAI | The Royal Institute of the Architects of Ireland |
| Security Management Plan | A plan that outlines the security requirements, threat assessments, risk mitigations and security controls necessary to protect information assets throughout the asset lifecycle in accordance with I.S.EN ISO 19650-5. |
| Scope | The defined boundary of work and deliverables that a party is required to provide under an agreement. It describes what is included and what is excluded, together with the outputs, quality/acceptance criteria, assumptions and constraints, interfaces, and any responsibilities needed to achieve the intended outcomes. |
| Task Team | A person or group of people performing a specific task – for example the drainage team or the subcontractor who is designing/constructing the vehicle restraint systems. |
| TIDP | Task Information Delivery Plan Schedule of Information Containers and delivery dates, for a specific Task Team. |
| TII | Transport Infrastructure Ireland Is a state agency in Ireland, dealing with road and public transport infrastructure. |
| TII NM | TII Network Management |
| Uniclass | Uniclass 2015 is a unified classification system for the construction industry covering all sectors of the industry. There are tables for civil and infrastructure projects covering road and rail, power and water. For the building sector there are tables including codes for university campuses, hospitals, schools, residential and office buildings. The codes are also there to cover landscape, structure and building services. |
| [Insert Here] | [Insert Here] |