## 1a Estimate Summary Sheet
TII Level 3 Estimate Summary Template
Insert Scheme Title:
Insert Date of Estimate:
Insert Current Phase:
Insert Consultants Name:
Insert Name of Estimator:
Insert Base Date for Rates:
1 | Main Construction Contract (MCC) - See Back up Summary Sheet for further breakdown |  |  |  | Total (€)
| Series 100 | Preliminaries
| Series 200 | Site Clearance
| Series 300 | Fencing and Environmental Noise Barriers
| Series 400 | Road Restraint Systems (Vehicles and Pedestrian)
| Series 500 | Drainage and Service Ducts
| Series 600 | Earthworks
| Series 700 | Pavements
| Series 1100 | Kerbs, Footways and Paved Areas
| Series 1200 | Traffic Signs and Road Markings
| Series 1300 | Road Lighting Columns and Brackets
| Series 1400 | Electrical Work for Road Lighting and Traffic Signs
| Series 1500 | Motorway Communications
| Series 1600 - 2300 | Structures
| Series 2500 | Special Structures
| Series 2700 | Watermains Utilities and Accommodation Works
| - | Landscaping
| - | Utilities Cost Estimates (Statutory Undertakers and Associated Civil Works)
| - | Other Costs
| - | Other Costs
| Total Base Cost for Main Construction Contract (Excluding VAT) |  |  |  | 0
| Add Project Specific Risk Contingency |  |  |  | %
| Sub-Total exclusive of VAT |  |  |  | 0
| Add VAT at |  |  |  | %
| Total MCC Base Cost plus Project Specific Risk Contingency and VAT |  |  |  | 0
2 | Land and Property
Base Cost Total from attached summary (to be compiled as per Appendix F Template)
Add Project Specific Risk Contingency
| Total L&P Base Cost plus Project Specific Risk Contingency |  |  |  | 0
3 | Planning and Design
Base Cost Total from attached summary (to be compiled based on Level 3 breakdown)
Add Project Specific Risk Contingency
| Total P&D Base Cost plus Project Specific Risk Contingency |  |  |  | 0
4 | Archaeology
Base Cost Total from attached summary (to be compiled based on Level 3 breakdown)
Add Project Specific Risk Contingency
| Total Archaeology Base Cost plus Project Specific Risk Contingency |  |  |  | 0
5 | Advance Works and Other Contracts
Base Cost Total from attached summary (to be compiled based on Level 3 breakdown)
Add Project Specific Risk Contingency
| Total Advance Works and Other Contracts Base Cost plus Project Specific Risk Contingency |  |  |  | 0
6 | Main Contract Supervision (Employer's Costs)
Base Cost Total from attached summary (to be compiled based on Level 3 breakdown)
Add Project Specific Risk Contingency
| Total MC Supervision (Employer's Costs) Base Cost plus Project Specific Risk Contingency |  |  |  | 0
7 | Residual Network (Provision to be subject to the approval of the TII Regional Manager)
Base Cost Total from attached summary (to be compiled based on Level 3 breakdown)
Add Project Specific Risk Contingency
| Total Residual Network Base Cost plus Project Specific Risk Contingency |  |  |  | 0
TOTAL LEVEL 3 ESTIMATE INCLUSIVE OF VAT |  |  |  |  | 0
| Mainline Length |  | km | Rate per km
| N.B. | Figures above are INCLUSIVE of VAT unless otherwise specified.
Figures above are EXCLUSIVE of provision for Inflation - base date to be stated if different from date of estimate.
Total base costs to include for ALL qualifying costs under each cost heading.
Refer to the TII Cost Management Manual and TII Requirements for Measurement and Pricing (RMP) for information on coverage and format of back-up.
See attached Back up to Summary Sheet for Further Scheme Information.

## 1b Summary Back Up Sheet
TII Estimate Back Up Summary Sheet
Scheme Name |  |  | Drg Library Ref. |  | TII Ref. |  | Estimate Date
Road Authority |  |  | Project Status |  |  |  | Region
Define any Project Specific Requirements in all rows below
Scheme Size | [9 empty] | Major | Minor
On-line | %
Off-line | % | [8 empty] | 10% | 20% | 30% | 40% | 50% | 60% | 70% | 80% | 90% | 100%
Location Type | [9 empty] | 10%: Urban; 20%: Suburban; 30%: Rural; 40%: Other (Please Specify)
Advanced Works carried out | [9 empty] | 10%: Yes; 20%: No
Proposed Contract Type | [9 empty] | 10%: PW-CF5; 20%: PW-CF3; 30%: PW-CF4; 40%: PPP; 50%: Other (Please Specify)
Anticipated Works programme duration | wks.
Remeasurable
Road Type
Project Specific Information
Mainline Scheme |  |  | Define any Project Specific Requirements in all rows below
Road Type |  | km | [7 empty] | Road Type 1 Single Carriageway | Road Type 2 Single Carriageway | Road Type 3 Single Carriageway | Road Type 3 Dual Carriageway | Road Type 2 Dual Carriageway | Road Type 1 Dual Carriageway
Side Roads |  | km
Grade Separated Junctions |  | Nr
Other |  | km
Series 200 - Site Clearance
General Site Clearance |  | ha
Demolition of Buildings or Structures |  | item
Other
Series 300 - Fencing and Environmental Noise Barriers | [9 empty] | 10%: Fencing
Boundary Fencing |  | m | [6 empty] | N/A | Timber Post & Rail Fence 1300mm H | Timber Post & Rail Stud Fence Type A 1350mm H | Timber Post & Rail Stud Fence Type B 1350mm High | Timber Post & Rail Stud Fence Type B 1350mm High | Concrete Post & Rail Fence 1400mm high | Timber Post & Wire Fence 1275mm high | Concrete Post & Mesh 1225mm high | Steel Palisade Security Fence
Other |  | m
Environmental Noise Barriers |  | m
Series 400 - Road Restraint Systems (Vehicles and Pedestrian)
Safety Barrier |  | m
Pedestrian Guardrail |  | m
Anti Glare Screens |  | m
Series 500 - Drainage and Service Ducts
Off road drainage |  | m
Attenuation areas |  | no
Outfalls |  | no
Concrete Channel |  | m
[10 empty] | Undulating | Flat
Series 600 - Earthworks
Earthworks cut / fill balance |  |  | Cut Quantity approx. | m3 |  | Re-usable Qty approx. |  | m3 |  | 10%: 35
Ground Conditions |  |  | Disposal Qty approx. | m3 |  | Imported Fill |  | m3 |  | 10%: 45
Terrain | [9 empty] | 10%: 50
Capping requirement |  | mm | [7 empty] | 50%: Safety Barrier
Imported Granular Material |  | m3 | [7 empty] | 10%: Traditional; 50%: Single sided safety barrier, Containment Level (N1), Impact Severity Level (A), Working width (W5), not exceeding 50m radius
Disposal of Material |  | m3 | [7 empty] | 10%: Design & Build; 50%: Single sided safety barrier, Containment Level (N2), Impact Severity Level (A), Working width (W2) straight or curved exceeding 120m radius
Unsuitable Material |  | m3 | [7 empty] | 50%: Single sided safety barrier, Containment Level (N2), Impact Severity Level (A), Working width (W4) straight or curved exceeding 120m radius
Rock |  | m3 | [7 empty] | 10%: Y; 50%: Single sided safety barrier, Containment Level (N2), Impact Severity Level (A), Working width (W5) straight or curved exceeding 120m radius
U1 / Peat |  | m3 | bar: 10%
?
Series 700 - Pavement | [9 empty] | 10%: Poor
Wearing course |  | mm | specify layer depth | [6 empty] | 10%: Favourable
Binder Course |  | mm | specify layer depth | bar: 10%
Base Course |  | mm | specify layer depth | [6 empty] | 10%: Flat
Series 1100 - Kerbs Footways and Paved Areas | [9 empty] | 10%: Poor
Footways & Paved Areas |  | m2
Cycleways |  | m2
Other
Series 1200 - Traffic Signs and Road Marking | [9 empty] | 10%: Poor
Traffic Signalling |  | Nr | [7 empty] | 20%: Pedestrian Crossing Non Signalled; 30%: Pedestrian Crossing Signalled; 40%: Typical Cross Roads traffic control system: using MOVA controls; 50%: Cycleway Traffic Lighting
Other
Series 1300 - Road Lighting Columns and Brackets | [9 empty] | 10%: Poor
Public Lighting Columns |  | Nr | [7 empty] | 20%: Pedestrian Crossing Non Signalled; 30%: Pedestrian Crossing Signalled; 40%: Typical Cross Roads traffic control system: using MOVA controls; 50%: Cycleway Traffic Lighting
Other
Series 1600 - 2300 Structures
Piped Culverts |  | no
Box Culverts |  | no
Overbridges |  | no
Pedestrian Footbridge |  | no
Underbridges |  | no
Signature Structures - Span |  | no
Other
Series 2700 - Watermains, Utilities and Accommodation Access Roads
Access Road Length to be specified |  | km
Access Road Width to be specified |  | m
Other
Landscaping
Landscaping including Topsoiling etc.. |  | m2

## 1c Back Up Tracker Sheet
TII Back Up Tracker Sheet
Level 3 Estimate Rev 1 |  |  | Level 3 Estimate Rev 2 |  |  | Level 3 Estimate Rev 3
Scheme Name |  |  | Scheme Name |  |  | Scheme Name
Drawing Library Refences |  |  | Drawing Library Refences |  |  | Drawing Library Refences
Estimate Date |  |  | Estimate Date |  |  | Estimate Date
Project Status |  |  | Project Status |  |  | Project Status
Mainline Scheme |  |  | Mainline Scheme |  |  | Mainline Scheme
Road Type |  | km | Road Type |  | km | Road Type |  | km | Road Type 1 Single Carriageway | Road Type 2 Single Carriageway | Road Type 3 Single Carriageway | Road Type 3 Dual Carriageway | Road Type 2 Dual Carriageway | Road Type 1 Dual Carriageway
Side Roads |  | km | Side Roads |  | km | Side Roads |  | km | Yes | No
Grade Separated Junctions |  | Nr | Grade Separated Junctions |  | Nr | Grade Separated Junctions |  | Nr
Other |  | km | Other |  | km | Other |  | km
Series 200 - Site Clearance |  |  | Series 200 - Site Clearance |  |  | Series 200 - Site Clearance
General Site Clearance |  | ha | General Site Clearance |  | ha | General Site Clearance |  | ha
Demolition of Buildings or Structures |  | item | Demolition of Buildings or Structures |  | item | Demolition of Buildings or Structures |  | item
Other |  |  | Other |  |  | Other
Series 300 - Fencing and Environmental Noise Barriers |  |  | Series 300 - Fencing and Environmental Noise Barriers |  |  | Series 300 - Fencing and Environmental Noise Barriers |  |  |  | Fencing
Boundary Fencing |  | m | Boundary Fencing |  | m | Boundary Fencing |  | m | N/A | Timber Post and Rail Fencing 1300mm High | Timber Post and Rail Stud Fencing Type A 1350mm High | Timber Post and Rail Stud Fencing Type B 1350mm High | Timber Post and Rail Stud Fencing Type B 1350mm High | Concrete Post and Rail Fencing 1400mm high | Timber Post and Wire Fence 1275mm high | Concrete Post and Mesh 1225mm high | Steel Palisade Security Fence
Other |  | m | Other |  | m | Other |  | m
Environmental Noise Barriers |  | m | Environmental Noise Barriers |  | m | Environmental Noise Barriers |  | m
Series 400 - Road Restraint Systems (Vehicles and Pedestrian) |  |  | Series 400 - Road Restraint Systems (Vehicles and Pedestrian) |  |  | Series 400 - Road Restraint Systems (Vehicles and Pedestrian)
Safety Barrier |  | m | Safety Barrier |  | m | Safety Barrier |  | m
Pedestrian Guardrail |  | m | Pedestrian Guardrail |  | m | Pedestrian Guardrail |  | m
Anti Glare Screens |  | m | Anti Glare Screens |  | m | Anti Glare Screens |  | m
Series 500 - Drainage and Service Ducts |  |  | Series 500 - Drainage and Service Ducts |  |  | Series 500 - Drainage and Service Ducts
Off road drainage |  | m | Off road drainage |  | m | Off road drainage |  | m | Fencing
Attenuation areas |  | no | Attenuation areas |  | no | Attenuation areas |  | no | Timber Post and Rail Fencing 1300mm High | Timber Post and Rail Stud Fencing Type A 1350mm High | Timber Post and Rail Stud Fencing Type B 1350mm High | Timber Post and Rail Stud Fencing Type B 1350mm High | Concrete Post and Rail Fencing 1400mm high | Timber Post and Wire Fence 1275mm high | Concrete Post and Mesh 1225mm high | Steel Palisade Security Fence
Outfalls |  | no | Outfalls |  | no | Outfalls |  | no
Concrete Channel |  | m | Concrete Channel |  | m | Concrete Channel |  | m
Series 600 - Earthworks |  |  | Series 600 - Earthworks |  |  | Series 600 - Earthworks
Earthworks cut / fill balance |  |  | Earthworks cut / fill balance |  |  | Earthworks cut / fill balance
| Cut Quantity approx. | m3 |  | Cut Quantity approx. | m3 |  | Cut Quantity approx. | m3
| Disposal Quantity approx. | m3 |  | Disposal Quantity approx. | m3 |  | Disposal Quantity approx. | m3
| Re-usable Quantity approx. | m3 |  | Re-usable Quantity approx. | m3 |  | Re-usable Quantity approx. | m3
| Imported Fill | m3 |  | Imported Fill | m3 |  | Imported Fill | m3
Ground Conditions |  |  | Ground Conditions |  |  | Ground Conditions
Terrain |  |  | Terrain |  |  | Terrain
Capping requirement |  | mm | Capping requirement |  | mm | Capping requirement |  | mm
Imported Granular Material |  | m3 | Imported Granular Material |  | m3 | Imported Granular Material |  | m3
Disposal of Material |  | m3 | Disposal of Material |  | m3 | Disposal of Material |  | m3 | Undulating | Flat
Unsuitable Material |  | m3 | Unsuitable Material |  | m3 | Unsuitable Material |  | m3
Rock |  | m3 | Rock |  | m3 | Rock |  | m3 | 35
U1 / Peat |  | m3 | U1 / Peat |  | m3 | U1 / Peat |  | m3 | 45
50
Series 700 - Pavement |  |  | Series 700 - Pavement |  |  | Series 700 - Pavement | [6 empty] | Safety Barrier
Wearing course | specify layer depth | mm | Wearing course | specify layer depth | mm | Wearing course | specify layer depth | mm | Traditional |  |  |  | Single sided safety barrier, Containment Level (N1), Impact Severity Level (A), Working width (W5), not exceeding 50m radius
Binder Course | specify layer depth | mm | Binder Course | specify layer depth | mm | Binder Course | specify layer depth | mm | Design & Build |  |  |  | Single sided safety barrier, Containment Level (N2), Impact Severity Level (A), Working width (W2) straight or curved exceeding 120m radius
Base Course | specify layer depth | mm | Base Course | specify layer depth | mm | Base Course | specify layer depth | mm |  |  |  |  | Single sided safety barrier, Containment Level (N2), Impact Severity Level (A), Working width (W4) straight or curved exceeding 120m radius
[9 empty] | Y |  |  |  | Single sided safety barrier, Containment Level (N2), Impact Severity Level (A), Working width (W5) straight or curved exceeding 120m radius
Series 1100 - Kerbs Footways and Paved Areas |  |  | Series 1100 - Kerbs Footways and Paved Areas |  |  | Series 1100 - Kerbs Footways and Paved Areas |  |  | N
Footways & Paved Areas |  | m2 | Footways & Paved Areas |  | m2 | Footways & Paved Areas |  | m2 | ?
Cycleways |  | m2 | Cycleways |  | m2 | Cycleways |  | m2 | Poor
Other |  |  | Other |  |  | Other |  |  | Favourable
?
Series 1200 - Traffic Signs and Road Marking |  |  | Series 1200 - Traffic Signs and Road Marking |  |  | Series 1200 - Traffic Signs and Road Marking |  |  | Flat
Traffic Signalling |  | Nr | Traffic Signalling |  | Nr | Traffic Signalling |  | Nr
Other |  |  | Other |  |  | Other |  |  | Poor
Series 1300 - Road Lighting Columns and Brackets |  |  | Series 1300 - Road Lighting Columns and Brackets |  |  | Series 1300 - Road Lighting Columns and Brackets
Public Lighting Columns |  | Nr | Public Lighting Columns |  | Nr | Public Lighting Columns |  | Nr
Other |  |  | Other |  |  | Other
Poor
Series 1600 - 2300 Structures |  |  | Series 1600 - 2300 Structures |  |  | Series 1600 - 2300 Structures |  |  |  | Pedestrian Crossing Non Signalled | Pedestrian Crossing Signalled | Typical Cross Roads traffic control system: using MOVA controls | Cycleway Traffic Lighting
Piped Culverts |  | no | Piped Culverts |  | no | Piped Culverts |  | no
Box Culverts |  | no | Box Culverts |  | no | Box Culverts |  | no
Overbridges |  | no | Overbridges |  | no | Overbridges |  | no | Poor
Pedestrian Footbridge |  | no | Pedestrian Footbridge |  | no | Pedestrian Footbridge |  | no |  | Pedestrian Crossing Non Signalled | Pedestrian Crossing Signalled | Typical Cross Roads traffic control system: using MOVA controls | Cycleway Traffic Lighting
Underbridges |  | no | Underbridges |  | no | Underbridges |  | no
Signature Structures - Span |  | no | Signature Structures - Span |  | no | Signature Structures - Span |  | no
Other |  |  | Other |  |  | Other
Series 2700 - Watermains, Utilities and Accommodation Access Roads |  |  | Series 2700 - Watermains, Utilities and Accommodation Access Roads |  |  | Series 2700 - Watermains, Utilities and Accommodation Access Roads
Access Road Length to be specified |  | km | Access Road Length to be specified |  | km | Access Road Length to be specified |  | km
Access Road Width to be specified |  | m | Access Road Width to be specified |  | m | Access Road Width to be specified |  | m
Other |  |  | Other |  |  | Other
Landscaping |  |  | Landscaping |  |  | Landscaping
Landscaping including Topsoiling etc.. |  | m2 | Landscaping including Topsoiling etc.. |  | m2 | Landscaping including Topsoiling etc.. |  | m2

## 2. Level 3 Estimate Tracker
TII Level 3 Estimate Tracker Comparison Sheet
| Scheme Name |  | Level 3 Estimate Rev 1 |  | Level 3 Estimate Rev 2 |  | Level 3 Estimate Rev 3
TII Ref
Estimate Date
Road Authority
| Project Status |  | Base Estimate |  | Uplift from Previous |  | Uplift from Previous
| Region |  | Date: |  | Date: |  | Date:
| Name of Consultant |  | Consultant: |  | Consultant: |  | Consultant:
|  |  | Estimator: |  | Estimator: |  | Estimator:
|  |  | Total € | Basis of Costs Estimate | Total € | Basis of Costs Estimate | Total € | Basis of Costs Estimate
1 | Main Construction Contract (See attached for breakdown presented to Level 3 detail)
| Series 100 | Preliminaries | 0 |  | 0 |  | 0 |  | ?
| Series 200 | Site Clearance | 0 |  | 0 |  | 0 |  | percentage based
| Series 300 | Fencing and Environmental Noise Barriers | 0 |  | 0 |  | 0 |  | Programme / Resourced based
| Series 400 | Road Restraint Systems (Vehicles and Pedestrian) | 0 |  | 0 |  | 0 |  | ?
| Series 500 | Drainage and Service Ducts | 0 |  | 0 |  | 0 |  | Lump Sum
| Series 600 | Earthworks | 0 |  | 0 |  | 0 |  | Measure and market Rate based
| Series 700 | Pavements | 0 |  | 0 |  | 0 |  | Historical Information
| Series 1100 | Kerbs, Footways and Paved Areas | 0 |  | 0 |  | 0 |  | First Principles Calculation
| Series 1200 | Traffic Signs and Road Markings | 0 |  | 0 |  | 0 |  | High Level Information
| Series 1300 | Road Lighting Columns and Brackets | 0 |  | 0 |  | 0 |  | N/A
| Series 1400 | Electrical Work for Road Lighting and Traffic Signs | 0 |  | 0 |  | 0
| Series 1500 | Motorway Communications | 0 |  | 0 |  | 0
| Series 1600 - 2300 | Structures | 0 |  | 0 |  | 0
| Series 2500 | Special Structures | 0 |  | 0 |  | 0
| Series 2700 | Watermains Utilities and Accommodation Works | 0 |  | 0 |  | 0
| - | Landscaping | 0 |  | 0 |  | 0
| - | Utilities Cost Estimates (Statutory Undertakers and Associated Civil Works) | 0 |  | 0 |  | 0
| - | Other Costs | 0 |  | 0 |  | 0
| - | Other Costs | 0 |  | 0 |  | 0
| Total Base Cost for Main Construction Contract (Excluding VAT) |  | 0 |  | 0 |  | 0
| Add Project Specific Risk Contingency |  | 0 |  | 0 |  | 0
| Sub-Total exclusive of VAT |  | 0 |  | 0 |  | 0
| Add VAT at |  | 0 |  | 0 |  | 0
| Total MCC Base Cost plus Project Specific Risk Contingency and VAT |  | 0 |  | 0 |  | 0
2 | Land and Property
| Base Cost Total from attached summary (to be compiled as per Appendix F Template) |  | 0 |  | 0 |  | 0
| Add Project Specific Risk Contingency |  | 0 |  | 0 |  | 0
| Total L&P Base Cost plus Project Specific Risk Contingency |  | 0 |  | 0 |  | 0
3 | Planning and Design
| Base Cost Total from attached summary (to be compiled based on Level 3 breakdown) |  | 0 |  | 0 |  | 0
| Add Project Specific Risk Contingency |  | 0 |  | 0 |  | 0
| Total P&D Base Cost plus Project Specific Risk Contingency |  | 0 |  | 0 |  | 0
4 | Archaeology
| Base Cost Total from attached summary (to be compiled based on Level 3 breakdown) |  | 0 |  | 0 |  | 0
| Add Project Specific Risk Contingency |  | 0 |  | 0 |  | 0
| Total Archaeology Base Cost plus Project Specific Risk Contingency |  | 0 |  | 0 |  | 0
5 | Advance Works and Other Contracts
| Base Cost Total from attached summary (to be compiled based on Level 3 breakdown) |  | 0 |  | 0 |  | 0
| Add Project Specific Risk Contingency |  | 0 |  | 0 |  | 0
| Total Advance Works and Other Contracts Base Cost plus Project Specific Risk Contingency |  | 0 |  | 0 |  | 0
6 | Main Contract Supervision (Employer's Costs)
| Base Cost Total from attached summary (to be compiled based on Level 3 breakdown) |  | 0 |  | 0 |  | 0
| Add Project Specific Risk Contingency |  | 0 |  | 0 |  | 0
| Total MC Supervision (Employer's Costs) Base Cost plus Project Specific Risk Contingency |  | 0 |  | 0 |  | 0
7 | Residual Network (Provision to be subject to the approval of the TII Regional Manager)
| Base Cost Total from attached summary (to be compiled based on Level 3 breakdown) |  | 0 |  | 0 |  | 0
| Add Project Specific Risk Contingency |  | 0 |  | 0 |  | 0
| Total Residual Network Base Cost plus Project Specific Risk Contingency |  | 0 |  | 0 |  | 0
TOTAL LEVEL 3 ESTIMATE INCLUSIVE OF VAT |  |  | 0 |  | 0 |  | 0
N.B. | Figures above are INCLUSIVE of VAT unless otherwise specified.
| Figures above are EXCLUSIVE of provision for Inflation - base date to be stated if different from date of estimate. |  | Mainline Length (km) |  | Mainline Length (km) |  | Mainline Length (km)
Total base costs to include for ALL qualifying costs under each cost heading.
| Refer to the TII Cost Management Manual and TII Reqs for Measurement and Pricing for information. |  | Rate per km |  | Rate per km |  | Rate per km
See attached Budget Assumptions Sheet for Further Scheme Information.

## 3. Estimating Guidelines
TII Estimating Guidelines for the development of a Level 3 Estimate
General Notes : |  | The Estimate template should use the main heading and sub-heading as TII's "Introduction to the Requirements for Measuring and Pricing" CC-RMP-00010 - January 2019.
Estimates at all levels of detail must include for risk and inflation. Where appropriate at Level 2 and in all cases at Level 3, these provisions must be separately identified.
No Provisional items shall be included in a Level 3 Estimate, details of any assumptions should be clearly outlined.
Users should refer to the TII RMP for guidance on typical itemisation that may be adopted when preparing Level 3 Estimates.
Unit Cost Estimates typically take the form of a priced bill of quantities - the level of itemisation will be subject to the amount of information available.
The basis of any rate included in a Level 3 Estimate should be available on request including rate build ups and assumptions used.
The user must determine if the TII Schedule of Rates have been used for developing Level 3 Estimates.
All Estimates must include for Value Added Tax (VAT) under all cost headings where appropriate. VAT provisions shall be separately identified under each cost heading.
The disclaimer at the bottom of the page must be ticked and signed by the user.
Cost Headings | Level 3 Estimate |  | Notes
Main Construction Contract | Series Section
| Series 100 | (i) Preliminaries
|  | Key Cost Elements to consider: | It is recommended that a programme based resourced schedule of Preliminaries including project specific requirements be considered and not just a percentage based calculation. It is also recommended that any temporary works be considered and incorporated into the estimate.
a. Mobilisation
b. Temporary Accommodation
c. Staffing Levels
d. Services and Resources for the Engineer
e. Demobilisation
|  | f. Temporary Works/Method Related Costs | It is recommended that the latest "Guidance for the Control and Management of Traffic at Road Works" and all other statutory requirements be considered when pricing Temporary Traffic Management.
|  | g. Other Preliminaries Costs | Other project specific Preliminaries costs should be clearly stated. |  | *
Key Cost Elements to consider:
|  | Programme of Works | A resourced based programme would be preferable with a task based being an alternative.
|  | Typical Employers Requirements | Should be clearly outlined and priced accordingly.
|  | Contractors typical Staffing schedule | Grade and applicable monthly cost to be provided.
(ii) Roadworks
| Series 200 | Site Clearance
|  | General | Is the lands made available indicated on the drawings, if so the full area should be measured for general site clearance.
|  | Specific, building to be demolished | Is there a schedule of building to be demolished, these should be described and numerated and priced accordingly.
|  | Other elements to be taken up for storage or disposal | An allowance should be made for other elements to be taken up, set aside or disposed of off site if required.
| Series 300 | Fencing and Environmental Noise Barriers | It is recommended that appropriate market rates are used to reflect a measure and to a considered standard construction details (SCD), considering access, topography and any specific ground conditions constraints. CC-RMP-00300 should be referred to in relation to the itemisation and coverage and pricing Fencing and Environmental Noise Barriers.
| Series 400 | Road Restraint Systems (Vehicles and Pedestrian) | It is recommended that appropriate market rates are used to reflect a measure and to a considered standard construction details (SCD), considering access, topography and any specific ground conditions constraints. CC-RMP-00400 should be referred to in relation to the itemisation and coverage and pricing Road Restraint Systems.
| Series 500 | Drainage and Service Ducts | It is recommended that appropriate market rates are used to reflect a measure and to a considered standard construction details (SCD), considering access, topography and any specific ground conditions constraints. It is recommended with the key items that first principles build up are used to reflect any considered constraints.CC-RMP-00500 should be referred to in relation to the itemisation, coverage and pricing Drainage and Service Ducts.
| Series 600 | Earthworks | It is recommended that a materials balancing exercise be carried out for the earthworks followed by a mass haul exercise to establish average haul distances, processing, importation/disposal of material. This should be followed up by costing the Earthworks from rates established from first principles considering the ground conditions, type and classification of material, processing, haulage and disposal/deposition of materials. CC-RMP-00600 should be referred to in relation to the itemisation, coverage and pricing Earthworks.
| Series 700 | Pavements | It is recommended that appropriate local market rates are used to reflect a measure and to considered standard depths of the pavement layers. CC-RMP-00700 should be referred to in relation to the itemisation, coverage and pricing Pavements.
| Series 1100 | Kerbs, Footways and Paved Areas | It is recommended that appropriate market rates are used to reflect a measure and to a considered standard construction details (SCD), considering access, topography and any specific ground conditions constraints. CC-RMP-01100 should be referred to in relation to the itemisation and coverage and pricing Kerbs, Footway and Paved Areas.
| Series 1200 | Traffic Signs and Road Markings | It is recommended that appropriate market rates are used to reflect a measure and to a considered standard signs etc. in line with Chapter 8 of Traffic Signs Manual, considering access, topography and any specific ground conditions constraints. CC-RMP-01200 should be referred to in relation to the itemisation and coverage and pricing Traffic Signs and Road Markings.
Main Construction Contract | Series 1300 | Road Lighting Columns and Brackets | It is recommended that appropriate market rates are used to reflect a measure and to a considered standard construction details (SCD), considering access, topography and any specific ground conditions constraints. CC-RMP-01300 should be referred to in relation to the itemisation and coverage and pricing Road Lighting Columns and Brackets.
| Series 1600-2300 | Structures | Due to the bespoke nature of Structures it is recommended that a full take off of the key elements of the structures be measure and priced in accordance with CC-RMP-01600-02300 considering all temporary works etc. At a minimum the costing of structures should be detailed and priced according to the deck area/length. It is strongly recommended that any deck area rate be used be in line with the market and the specific design of the structure.
| Series 2700 | Watermains, Utilities and Accommodation Works | It is recommended that appropriate market rates are used to reflect a measure and to a considered standard construction details (SCD), considering access, topography and any specific ground conditions constraints. It is recommended with the key items that first principles build up are used to reflect any considered constraints.CC-RMP-02700 should be referred to in relation to the itemisation, coverage and pricing Watermains.
| - | Landscaping | The method of measurement used for measurement and pricing of Series 3000 Landscaping should be clearly defined and the rates used are to be in line with market rates.
| - | Utilities Cost Estimates (Statutory Undertakers and Associated Civil Works)
|  | Accommodation Works | Back-up is required on a plot by plot basis, identifying name and location of land owner.
|  | Statutory Undertakers Works | Works to be identified in relation to all service providers affected by the works - list should include where appropriate provision for:
- Gas
- Water
- Foul Drainage
- Electricity - Distribution
- Electricity - Local service
- Telecoms
- Data Transmission Cabling
|  | Risk (Allocated where possible to key risks) | Risk provision must be based on a Quantitative Risk Analysis supported by a detailed Risk Register
|  | Inflation | Inflation projection to be accompanied by rates utilised and construction timeframe applied Expenditure profile to be provided in support of calculation.
Site Supervision (Client) |  | Actual costs and contract amounts where known supplemented by a unit cost estimate combining elemental provisions where necessary broken down to the following level of detail: | a. Off-site Project Management Provision
b. On-Site Works Management Provision
c. Risk
d. Inflation
Costs include qualifying NRDO and/or Local Authority Costs as well as Engineering Consultant's staff and associated expenses where applicable. Such costs include off-site design and/or supervision support.
Roles may include Client Supervisor; Client Representative or Engineer and supporting staff under the Contract.
Costs could include specialist advice and/or services in relation to legal matters; disputes resolution or utilities advice.
Costs may include supervision of works contracts other than the main construction contract where occurring after the commencement of the main construction contract.
From Phase 3, the estimate should be based on a schedule of agreed staff numbers, grade and rates.
Disclaimer | For the development of a Level 3 Estimate, the user must read and gain an understanding of the relevance of all information contained in the TII Estimating Guidelines above. The user must tick the box and sign off to confirm they have read the guidelines above and have a detailed knowledge of the type of work contemplated and the factors which impact on the cost of executing such work. |  |  | Signature: ….............................................................................................
NO
YES

## 4. Ticksheet & Checklist
TII Guidelines for checking a Level 3 MCC Estimate
Main Construction Contract (See attached for breakdown presented to Level 3 detail) |  | Series Section Priced | Cost back up information provided | Item Included Yes/No | Item measured in accordance with the RMP | 2019 TII Schedule of Rates Used | Other Basis of Rate Formulation (If so please define in comments section) | Standard Construction Detail (SCD) used | Comments | Y
Series 100 | Preliminaries | [8 empty] | N
Preliminaries calculated on a percentage basis
Preliminaries calculated based on a indicative Programme
Preliminaries costed on the basis of a priced resourced schedule
if Yes have the following elements been considered:
a. Mobilisation
b. Temporary Accommodation
c. Staffing Levels
d. Services and Resources for the Engineer
e. Demobilisation
f. Temporary Works
g. All other Preliminaries Costs
Other items not included above, please define and schedule in comments column
Series 200 | Site Clearance
General
Demolition of individual or groups of buildings or structures
Partial demolition of individual structures
Other items not included above, please define and schedule in comments column
Series 300 | Fencing and Environmental Noise Barriers
Fencing, Gates and Stiles
Walls and Environmental Noise Barriers
Other items not included above, please define and schedule in comments column
Series 400 | Road Restraint Systems (Vehicles and Pedestrian)
Safety Barrier System
Vehicle Parapet Systems
Pedestrian Parapets, Pedestrian Guardrails and Handrails
Other items not included above, please define and schedule in comments column
Series 500 | Drainage and Service Ducts
Drains, Sewers, Piped Culverts and Service Ducts (Excluding Filter Drains, Narrow Filter Drains & Fin Drains)
Filter Drains
Fin Drains and Narrow Filter Drains
Connections
Chambers and Gullies
Headwalls and Outfall Works
Soft Spots and Other Voids
Excavation in Hard Material
Other items not included above, please define and schedule in comments column
Series 600 | Earthworks
Excavation, Deposition & compaction of fill balance
Acceptable material Class 5A
Acceptable material excluding Class 5A
Unacceptable material Class U1
Unacceptable material Class U2
Excavation in Hard Material
Disposal of Fill
Imported Fill
Soil Improvement
Geotextiles
Soft Spots and Other Voids
Excavation in Hard Material
Other items not included above, please define and schedule in comments column
Series 700 | Pavements
Sub-base Pavement
Regulating Course
Surface Treatment
Bond Coat
Cold Milling
Repave Recycle Process
Reinstatement of Paved Areas
Repairs to Existing Concrete Carriageway
Geotextiles and Geotextile-related products
Repair Systems
Other items not included above, please define and schedule in comments column
Series 1100 | Kerbs Footways and Paved Areas
Kerbs, Channels, Edgings, Combined Drainage and Kerb Blocks and Linear Drainage Channel Systems
Additional Concrete for Kerbs, Channels, Edgings, Combined Drainage and Kerb Blocks and Linear Drainage Channel Systems
Remove from Store and Relay Kerbs, Channels, Edgings and Combined Drainage and Kerb Blocks
Footways and Paved Areas
Remove from Store and Relay Paving Flags and Blocks Steps Remove from Store and Re-erect Street Furniture
Other items not included above, please define and schedule in comments column
Series 1200 | Traffic Signs and Road Markings
Traffic Signs
Road Markings
Other items not included above, please define and schedule in comments column
Series 1300 | Road Lighting Columns and Brackets
Road Lighting Columns, Brackets and Wall Mountings
Remove from Store and Re-erect Road Lighting Columns, Brackets and Wall Mountings
Other items not included above, please define and schedule in comments column
Series 1600-2300 | Structures
Deck area measure/rate used
First principles build up used
Other items not included above, please define and schedule in comments column
Series 2700 | Watermains, Utilities and Accommodation Works
Watermains
Utilities (other than Watermains)
Accommodation Works
Other items not included above, please define and schedule in comments column
- | Landscaping
- | Utilities Cost Estimates (Statutory Undertakers and Associated Civil Works)
Other Costs
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
Low
Med
High
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes
no
yes

## 5. Guide for checking Estimates
TII High Level Guidelines for checking
a Level 3 MCC Estimate
Guidance Notes
1 | Ensure all information has been inserted by the user in datasheets (1 - 4) and no cells have been left (Red) i.e. incomplete. Where applicable the user should have selected from the drop down menu provided and outlined any other project specific requirements.
2 | Check which rates have been used in the Tick sheet and Checklist under section heading " TII 2019 Schedule of rates Used". The user must either tick whether they used a low, medium or high rate from the SOR for each of the series sections. If other rates have been selected the user must define the basis of the rates used.
3 | Datasheet 1a "TII Level 3 Estimate Summary Sheet" - The total cost must be inserted by the user on the Main Construction Cost (MCC) Summary sheet. The project specific information must also be clearly indicated at top of the page including: Title, Date of estimate, Current phase, Consultant name, Name of Estimator and Base Date for Rates. Project specific risk and contingency and all other additional costs exclusive of the MCC must be clearly defined.
4 | Datasheet 1b "TII Estimate Back Up Summary Sheet" - It is essential that the user outlines the drawings Library references used for the purposes of developing the Level 3 Estimate. TII can then track the batch of drawings used for any updated or revised estimates issued. The user must insert a cell entry from the drop down menus provided. If any remaining cells are still in red these items are deemed non compliant and should be revisited by the user. It is not mandatory for the user to enter any project specific requirements in the "Project Specific Requirements" comments section to the side. This should be only compiled where deemed necessary.
5 | Datasheet 1c " Back Up Tracker Sheet" - Similar to note 3 above. Once all project specific information is included, this spreadsheet can be used to evaluate and compare against any previous or updated estimate revisions. The details of the key cost items for each series sections must be comparable. This will highlight if there has been a change to the scope of works or a design addition / omission. For example if the Pavement build up depths have changed.
6 | Datasheet 2 " Level 3 Estimate Tracker" - The total cost of each Series Section is included in this spreadsheet and can be used to evaluate and compare against any previous or updated estimate revisions. Future inflation should be considered at this stage based on the date the estimate was completed. The user must insert a cell entry from the drop down menus provided. For example he/she must outlined if the Series 100 - Preliminaries was priced on a percentage basis or programme resourced based. If any remaining cells are still in red these items are deemed non compliant and should be revisited by the user.
7 | Datasheet 3 " Estimating Guidelines" - The disclaimer at the bottom of the page must be completed. This will ensure that the user has read and considered all information contained in the TII Estimating Guidelines. The user must confirm they have read the guidelines above and have a detailed knowledge of the type of work contemplated and the factors which impact on the cost of executing such work. The guideline will help the estimator to consider project specific variables when pricing an estimate. For example when pricing Series 600 Earthworks the rates should where possible be established from first principles considering the ground conditions, type and classification of material, processing, haulage and disposal/deposition of materials.
8 | Datasheet 4 " Ticksheet & Checklist" - This section must be completed by the user and will highlight if each series section has considered the following: - Series Section Priced (Yes/No) - Cost back up information provided (Yes/No) - Item Included (Yes/No) - Item measured in accordance with the RMP (Yes/No) - 2019 TII Schedule of Rates Used (Low, Medium or High) - Other Sourced Rates used (Yes/No) - Standard Construction Detail used (Yes/No)