## Appendix A0 Cost headings
TII Cost Management Manual – Cost Heading Coverage and Minimum Detail Required in Support of Project Cost Estimates
Notes:
1. Appendix A0 will be read in conjunction with the balance of the Cost Management Manual.
2. Estimates at all levels of detail must include for risk and inflation. At Level 2 and, in all cases, at Level 3 these provisions must be separately identified.
3. Level 1 and Level 2 estimates must include provision for all items to be separately provided for in a Level 3 estimate.
4. Users may refer to the TII Requirements for Measurement and Pricing for guidance on typical itemisation that may be adopted when preparing Level 3 estimates.
5. Unit cost estimates typically take the form of a priced bill of quantities – the level of itemisation will be subject to the amount of information available.
6. Unit cost estimates can contain lump sum provisions or elemental costs for items where information is insufficient to allow quantification.
7. All estimates must include for Value Added Tax (VAT) under all cost headings where appropriate. VAT provisions will be separately identified under each cost heading.
Cost Headings | Level 1 Estimate | Level 2 Estimate | Level 3 Estimate | Notes
1. Planning and Design | Percentage of Main Construction Cost Estimate based on historical date for similar services and Projects. | As per Level 1 amended to reflect actual costs / contract amounts where known. | Actual costs and contract amounts where known, supplemented where necessary by a unit cost estimate based on resources and durations combining elemental provision where necessary - broken down to the following level of detail: | Planning and Design includes Option Selection; Constraints Studies --- Design; Land Acquisition Documentation, and Oral Hearing Costs.
|  |  | 1. Design. | These costs include qualifying Sponsoring Agency and NRDO costs in addition to Technical Advisor Fees incurred between Phases 1 and 5 including supervision of enabling works contracts.
|  |  | 2. Planning. | From Phase 3, the estimate should be based on a schedule of agreed staff numbers, grade and rates for each envisaged planning and design contract.
3. Surveys.
4. Site Investigation.
5. Environmental Impact Statement.
6. Tender Documentation, Tender Process, and Contract Award.
7. Any Other Relevant Costs.
8. Risk.
9. Inflation.
2. Land and Property | Elemental estimate based on local all-in rates per hectare for development and agricultural land plus property cost estimate. | Unit Cost estimate based on Land Valuers Report including rates per acre for different land zonings and individual property prices where quantifiable. | Actual costs where known, supplemented by a unit cost estimate based on acreage per plot and price per property combining elemental provisions – where necessary broken down to the following level of detail: | Area in hectares, owners and use for valuation purposes to be identified plot by plot. Fees include Valuers; Legal and other Technical Advisors.
|  |  | 1. Land. | Excludes Costs for Land Acquisition Mapping and Oral Hearing Costs.
2. Property.
3. Land Agents Fees (Sponsoring Agency and Claimant Fees).
4. Other Professional Fees (Sponsoring Agency and Claimant Fees).
5. Injurious Affection and Severance.
6. Disturbance.
7. Reinvestment Costs.
8. Accommodation Works (including payment in lieu).
9. Clause 12 Payments.
10. Sponsoring Agency Disputes Resolutions Costs.
11. Any Other relevant costs.
12. Risk.
13. Inflation.
3. Archaeology | Percentage of Main Construction Cost Estimate. | As per Level 1 amended to reflect actual costs / contract amounts where known. | Actual costs and contract amounts where known, supplemented by a unit cost estimate combining elemental provisions where necessary - broken down to the following level of detail: | Costs include any direct payments to Archaeological Advisors of Contractors engaged to carry out Archaeological Investigations and / or Excavations.
|  |  | 1. Archaeology Surveys | Costs exclude archaeology supervision or excavation to be carried out by the Main Contractor under the main construction contract – provision for such costs must be made in the main construction cost estimate.
|  |  | 2. Costs for other specified Archaeological activities. | From Phase 3, the archaeology estimate should be based on a schedule of resources and durations for defined activities such as excavation, resolution and post-resolution publication priced using unit rates.
3. Risk.
4. Inflation.
4. Enabling Works and Other Contracts | Percentage of Main Construction Cost Estimate. | As per Level 1 amended to reflect actual costs / contract amounts where known. | Actual costs and contract amounts where known, supplemented by unit cost estimate combining elemental cost provisions – where necessary broken down to the following level of detail: | Any construction work other than the main construction contract must be allowed for under this heading (whether in advance, in tandem with or following substantial completion).
|  |  | 1. Service diversions. | Where applicable, provision for the interface with enabling works contracts is typically included within the main construction cost estimate.
2. Ground Stabilisation of Advance Safety Works.
3. Fencing.
4. Environmental Works.
5. Hedgerow Clearance and Landscaping.
6. Artistic features.
7. Accommodation Works.
8. Other Enabling or Finishing Works or miscellaneous works contracts.
9. Risk.
10. Inflation.
5. Main Construction Contract | Elemental Estimate to be prepared to level of detail based on information available which must be as outlined as below. | Combined elemental and unit cost estimate broken down to the level of detail outlined below. | Unit cost estimate with elemental provisions, where necessary broken down to the level of detail outlined below. Once the main construction contract has been tendered, the winning tender amount will constitute the base cost for the Level 3 estimate. | Risk and Inflation provisions must be calculated and included for in relation to all main construction contract cost provisions.
| Breakdown anticipated to differentiate between Roadworks and Structures Costs. | Where tunnelling or other specialist construction solutions are deemed necessary, these will be separately identified and similarly broken down. | Where tunnelling or other specialist construction solutions are deemed necessary, these will be separately identified and similarly broken down. | Final cost under this heading following the completion of the construction works will be the Main Construction Contract Final Account.
| Where tunnelling or other specialist construction solutions are believed to be necessary, these will be separately identified within the estimate. | Specialist M&E measures, for example, will similarly be identified and broken down. | Specialist M&E or other untypical measures will be similarly identified and broken down. | Provision for archaeology to be carried out but the Main Contractor is typically addressed within the risk provision.
| Where key risks are known, the estimate should detail the provisions made for same. | 1. Preliminaries: | 1. Preliminaries: | Where applicable, provision for the interface with enabling works contracts is typically included within the main construction contract estimate.
| Where it is anticipated that multiple funders may be involved in a project the cost estimates should clearly identify the elements of work costs associated with each funder. | a. Temporary Works / Method Related Costs. | a. Mobilisation. | Mainline roadworks may include national and / or non-national routes.
|  | b. All other Preliminaries Costs. | b. Temporary Accommodation. | At Level 3, Interchange Costs should be shown separately as indicated and ideally for all costs.
|  | 2. Roadworks – Mainline: | c. Staff. | Include provision here for footpaths and roadworks where not included under roadworks.
| Estimate to include for and to identify basis of provision for inflation and risk. | a. Earthworks Cut and Fill. | d. Services and Resources for the Engineer. | New Works and Diversions must be separately identified.
| 1. Roadworks back-up to outline basis of rate per km. | b. Pavement Area. | e. Demobilisation.
| 2. Structures back-up to outline basis of rate per structure. | c. Other Costs. | f. Temporary Works / Method Related Costs.
| 3. Interchanges or junction provisions to be separately identified with back-up to outline basis of rate per item. | 3. Roadworks – Interchanges: | g. All other Preliminaries Costs.
| 4. Specialist Construction Solution including tunnels and Signature Structures to be separately identified with back-up to rates and prices. | a. Earthworks Cut and Fill. | 2. Roadworks – Mainline:
| 5. Treatment of Risk and Inflation to be outlined. | b. Pavement Area. | Including interchanges unless noted under 3 below.
|  | c. Other Costs. | a. Site clearance.
|  | 4. Roadworks – Sideroads: | b. Fencing and environmental barriers.
|  | As per 2. Roadworks – Mainline above. | c. Safety fences and Pedestrian Guardrails.
|  | 5. Structures: | d. Drainage and Ducting.
|  | a. Identify Structures Separately. | e. Earthworks.
|  | b. Quantify deck area per structure. | f. Pavement.
|  | c. Identify separate provisions where applicable for: | g. Kerbs, Footways, and Paved Areas.
|  | i. Special preliminaries including Temporary Works. | h. Traffic Signs.
|  | ii. Special Foundations. | i. Roadmarking.
|  | iii. Rail, River or Canal Crossings. | j. Lighting and Electrical Work.
|  | 6. Accommodation Works: | k. Landscaping and Environmental.
|  | a. Basis of provision per km/m of carriageway. | l. Communications and Technology.
|  | 7. Statutory Undertakers Works: | m. All other costs.
|  | a. Basis of provision per km/m of carriageway. | 3. Roadworks – Interchanges:
|  | 8. Risk (Allocated where possible to key risks): | a. Drainage and Ducting.
|  | Provide basis of risk provision calculation. | b. Earthworks.
|  | 9. Inflation: | c. Pavement.
|  | Inflation projection to be accompanied by rates utilised and construction timeframe applied. | d. Kerbs, Footways, and Paved Areas.
|  | Expenditure profile to be provided in support of calculation. | 4. Roadworks – Side Roads:
As per 2 Roadworks – Mainline above.
5. Structures:
(Information required in relation to each structure)
a. Special Preliminary Requirements:
i. Temporary Works.
b. Foundations:
i. Piling.
c. Substructures – End and Intermediate Supports.
d. Superstructure.
e. Finishings:
i. Special Features (e.g. Architectural Lighting).
f. Rail, River, or Canal Crossings.
6. Accommodation Works:
a. Back-up required on a plot by plot basis.
Identify works required in accordance with level of detail for roadworks and structures.
7. Statutory Undertakers Works:
Works to be identified in relation to all service providers affected by the works – list should include where appropriate provision for:
i. Gas
ii. Water
iii. Foul Drainage
iv. Electricity – Distribution.
v. Electricity – local Service.
vi. Telecoms
vii. Data Transmission Cabling.
8. Risk (Allocated where possible to key risks):
Risk provision must be based on a Quantitative Risk Analysis supported by a detailed Risk Register.
9. Inflation:
Inflation projection to be accompanied by rates utilised and construction timeframe applied.
Expenditure profile to be provided in support of calculation.
6. Site Supervision | Percentage of the Main Construction Cost Estimate. | As per Level 1 amended to reflect actual costs / contract amounts where known. | Actual costs and contract amounts where known, supplemented by a unit cost estimate combining elemental provisions - where necessary broken down to the following level of detail: | Costs include qualifying NRDO and / or Sponsoring Agency Costs as well as Technical Advisor’s staff and associated expenses where applicable. Such costs include off-site design and / or supervision support.
|  |  | 1. Off-site Project Management Provision. | Roles may include Client Supervisor; Client Representative or Engineer and supporting staff under the Contract.
|  |  | 2. On-Site Works Management Provision. | Costs could include specialist advice and / or services in relation to legal matters; dispute resolution or utilities advice.
|  |  | 3. Risk. | Costs may include supervision of works contracts other than the main construction contract where occurring after the commencement of the main construction contract.
|  |  | 4. Inflation. | From Phase 3, the estimate should be based on a schedule of agreed staff numbers, grade and rates.
7. Walking / Cycling / PT Connectivity / Asset Renewal | Percentage of Main Construction Cost Estimate. | As per Level 1 amended to reflect actual costs / contract amounts where known. | Subject to availability of information, a combined elemental and unit cost estimate broken down to the level of detail outlined below and amended to reflect actual costs and contract amounts where known: | This heading is for costs associated with repair of/or remedial works to the local roads network and other minor works that may be necessary on foot of the main contract.
1. Additional Signage.
2. Repairs to existing roads resultant from undertaking works.
3. Contribution to repair of existing roads.
4. Appropriate works to facilitate walking / cycling and / or public transport connectivity
5. Any other relevant costs.
6. Risk.
7. Inflation.
See heading 5 above for level of detail required in relation to each element of Walking / Cycling / PT Connectivity / Asset Renewal network works.
Note on E118: Michael Gaughan: Upgrading” ?? Can TII legally spend funding on upgrading a regional or local road not forming part of a scheme? I have never had a project that allows for separate upgrade of local road network

## Appendix A1_Lvl 1 Est Summary
See Separate Sheet

## Appendix A1a_Lvl 1 FWC
See Separate Sheet

## Appendix A2_Lvl 2 Est Summary
See Separate Sheet

## Appendix A2a_Lvl 2 Backup
See Separate Sheet

## Appendix A3 Level 3 Estimate
Refer to current revision of PE-PMG-02044-01_Appendices Workbook 2 of 2.

## Appendix A4_MinPrj TC1
See Separate Sheet

## Appendix A5 Option Comparison
See Separate Sheet

## Appendix A6 TC, TSB (Minors) (hidden)
ROUTE No. | [5 empty] | Date
SCHEME NAME | [5 empty] | PRS No
Road Authority | [6 empty] | Region?
Tick Appropriate Box
Estimate Only (sheet not signed) |  | Budget at Appraisal (TC1) |  |  | Budget prior to Tender Issue (TC2) |  | Budget at Tender Award (TC3) |  | Outturn Costs
Scheme Description
Scheme Programme, Status and Appraisal (when available)
Programme |  | Stage /Activity |  |  |  | Start [mm/yyyy] |  |  | Completion [mm/yyyy]
Design
EIS / NIS
CPO
Tender
Construction
Scheme Status |  | Land Acquisition
Planning Status
Appraisal |  | Status | [6 empty] | BCR
Approvals Granted |  | Undertake Detailed Design/Appraisal
Proceed to CPO/Purchase Land
Award Construction Tender
0
Base Cost Expenditure Heading |  | Base Cost (incl VAT) | Contingency | Contingency % | Budget € | Yearly Profiles (Euro)
[6 empty] | Pre 2018 | 2018 | 2019 | 2020 | Post 2020
Check Totals
Main Contract Construction |  |  |  | #DIV/0! | 0 | [11 empty] | Month | Archaeology | 0
Main Contract Supervision |  |  |  | #DIV/0! | 0 | [6 empty] | Planning & Design (incl GI & Topo) |  |  |  |  | Dec'12 | 11212 | 0
Archaeology |  |  |  | #DIV/0! | 0 | [6 empty] | Year | MNRPO | Jacobs | Check Sums |  | Jan'13 | 4360 | 0
Advance Works & Other Contracts |  |  |  | #DIV/0! | 0 | [6 empty] | 2011 | 162205 | 109181 | 271386 |  | Feb'13 | 6794 | 0
Residual network |  |  |  | #DIV/0! | 0 | [6 empty] | 2012 | 212723 | 193017 | 405740 |  | Mar'13 | 3089 | 0
Land & Property |  |  |  | #DIV/0! | 0 | [6 empty] | 2013 | 42000 | 230800 | 272800 |  | Apr'13 | 12 | 0
Planning & Design (incl GI & Topo) |  |  |  | #DIV/0! | 0 | [13 empty] | 0
TOTAL |  | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2015 | 42000 | 12433 | 54433 | Close-Out | June'13 | 8991 | 0
Programme Risk | [7 empty] | 0 |  |  |  | Total | 458928 | 545431 | 1004359 |  | Total | 34458
SCHEME BUDGET | [7 empty] | 0
SCHEME NAME | 0 | [7 empty] | PRS No | 0
Top Risks Considered under Main Contract Construction
|  | Risk # |  |  |  | Risk Description |  |  |  | Overall Impact
1
(and potential impact) |  | 2
3
4
5
6
7
8
9
10
|  | 11 | [7 empty] | 0
12
Total
Engineering Inspector:_________________________ Date:__________
Regional Manager:____________________________ Date:__________
Head of Roads Capital Programme:_______________________ Date:__________
Project Services:______________________________ Date:__________
Director of Capital Programme:__________________________ Date:__________
Chief Executive:_______________________ Date:___________
Note on P42: Richard Glancy: Jacob's MFC Fee = €602,781. Change Orders Estimate €20,000 TOTAL = €622,781.00
Note on V42: Richard Glancy: Expenditure 2013 Year to-date None anticipated for the remainder of the year.

## Appendix A6_MajPrj TSB
See Separate Sheet

## Appendix A6a_RCF Record
See Separate Sheet

## Appendix A7 Estimate Assumption
See Separate Sheet

## Appendix A8 Change Order Re
Change Order Register
Project :
TII Reference :
Instruction Reference | Date of Instruction | Brief Description | Reason for Change Order | Impacted Works Element | Delay Event (Y/N/TBC) | Compensation Event (Y/N/TBC)

## Appendix A9 Typical Pricing
Breakdown of Tender Total (for Typical Design and Build Contract)
Item | Description | Sum(Euro)
1.0 | Preliminaries
1.1 | Mobilisation
1.2 | Staff
1.3 | Servicing of Accommodation
1.4 | Traffic Management
1.5 | Demobilisation
1.6 | Balance of Preliminaries
1.0 | Preliminaries Total to Tender Summary
2.0 | Site Clearance
2.1 | Structures - National Roads including Interchanges
2.2 | Structures - All Other Roads including Interchanges
2.3 | Balance of Site Clearance - National Roads including Interchanges
2.4 | Balance of Site Clearance - All Other Roads including Interchanges
2.0 | Site Clearance Total to Tender Summary
3.0 | Fencing (excluding Safety Barriers)
3.1 | Environmental Barriers - National Roads Including Interchanges
3.2 | Environmental Barriers - All Other Roads Including Interchanges
3.3 | Balance of Fencing - National Roads Including Interchanges
3.4 | Balance of Fencing - All Other Roads Including Interchanges
3.0 | Fencing Total to Tender Summary
4.0 | Safety Barriers and Pedestrian Guardrails
4.1 | Safety Barriers - National Roads Including Interchanges
4.2 | Safety Barriers - All Other Roads Including Interchanges
4.3 | Pedestrian Guardrails - National Roads Including Interchanges
4.4 | Pedestrian Guardrails - All Other Roads Including Interchanges
4.0 | Safety Barriers and Pedestrian Guardrails Total to Tender Summary
5.0 | Drainage and Service Ducts
5.1 | Drainage - National Roads excluding Interchanges
5.2 | Drainage - National Roads Interchanges
5.3 | Drainage - Regional Roads Including Interchanges
5.4 | Drainage - All Other Roads
5.5 | Service Ducts - National Roads excluding Interchanges
5.6 | Service Ducts - National Roads Interchanges
5.7 | Service Ducts - Regional Roads Including Interchanges
5.8 | Service Ducts - All Other Roads
5.0 | Drainage and Service Ducts Total to Tender Summary
6.0 | Earthworks
6.1 | Earthworks - National Roads excluding Interchanges
6.2 | Earthworks - National Roads Interchanges
6.3 | Earthworks - Regional Roads Including Interchanges
6.4 | Earthworks - All Other Roads
6.5 | Earthworks - Watercourses
6.0 | Earthworks Total to Tender Summary
7.0 | Pavement
7.1 | Sub-Base - National Roads excluding Interchanges
7.2 | Sub-Base - National Roads Interchanges
7.3 | Sub-Base - Regional Roads Including Interchanges
7.4 | Sub-Base - All Other Roads
7.5 | Roadbase - National Roads excluding Interchanges
7.6 | Roadbase - National Roads Interchanges
7.7 | Roadbase - Regional Roads Including Interchanges
7.8 | Roadbase - All Other Roads
7.9 | Basecourse - National Roads excluding Interchanges
7.10 | Basecourse - National Roads Interchanges
7.11 | Basecourse - Regional Roads Including Interchanges
7.12 | Basecourse - All Other Roads
7.13 | Wearing Course - National Roads excluding Interchanges
7.14 | Wearing Course - National Roads Interchanges
7.15 | Wearing Course - Regional Roads Including Interchanges
7.16 | Wearing Course - All Other Roads
7.0 | Pavement Total to Tender Summary
8.0 | Kerbs, Footways and Paved Areas
8.1 | Kerbs to National Roads Including Interchanges
8.2 | Kerbs to All Other Roads
8.3 | Footways and Paved Areas to National Roads Including Interchanges
8.4 | Footways and Paved Areas to All Other Roads
8.0 | Kerbs, Footways and Paved Areas Total to Tender Summary
9.0 | Traffic Signs
9.1 | Traffic Signs to National Roads Including Interchanges
9.2 | Traffic Signs to All Other Roads
9.3 | Traffic Signs to National Roads Including Interchanges
9.4 | Traffic Signs to All Other Roads
9.0 | Traffic Signs Total to Tender Summary
10.0 | Road Markings
10.1 | Road Markings to National Roads Including Interchanges
10.2 | Road Markings to All Other Roads
10.3 | Road Markings to National Roads Including Interchanges
10.4 | Road Markings to All Other Roads
10.0 | Road Markings Total to Tender Summary
11.0 | Lighting and Electrical Work
11.1 | Lighting and Electrical Work to National Roads Including Interchanges
11.2 | Lighting and Electrical Work to All Other Roads
11.3 | Lighting and Electrical Work to National Roads Including Interchanges
11.4 | Lighting and Electrical Work to All Other Roads
11.0 | Lighting and Electrical Work Total to Tender Summary
12.0 | Landscaping and Environmental Works
12a | Landscaping to National Roads
12b | Landscaping to All Other Roads
12c | Environmental Work to National Roads
12d | Environmental Work to All Other Roads
12.0 | Landscaping and Environmental Works Total to Tender Summary
13.0 | Structures (EXPAND LISTING AS REQUIRED)
13.1 | Structure 1 - Foundations and Sub-Structure
13.2 | Structure 1 - Superstructure
13.3 | Structure 1 - Finishes
13.4 | Structure 2 - Foundations and Sub-Structure
13.5 | Structure 2 - Superstructure
13.6 | Structure 2 - Finishes
13.7 | Structure 3 - Foundations and Sub-Structure
13.8 | Structure 3 - Superstructure
13.9 | Structure 3 - Finishes
13.10 | Culverts (>= 900mm Diameter)
13.11 | Retaining Walls
13.0 | Structures Total to Tender Summary
14.0 | Accommodation Works
14.1 | Construction of Accommodation Works Access Roads
14.2 | Balance of Accommodation Works
14.0 | Accommodation Works Total to Tender Summary
15.0 | Works (Including Main Works) for Statutory Authorities, Public and Private Utilities Companies and Organisations, Service Providers and Other Companies (EXPAND LISTING AS REQUIRED)
15.1 | ESB and all associated and affiliated companies
15.1a | Diversion Works for ESB
15.1b | Main Works for ESB
Sub-Total
15.2 | Eircom
15.2a | Diversion Works for Eircom
15.2.b | Main Works for Eircom
Sub-Total
15.0 | Works (Including Main Works) for Statutory Authorities, Public and Private Utilities Companies and Organisations, Service Providers and Other Companies Total to Tender Summary
16.0 | Any Other Obligations and Liabilities of the Contractor
16.1 | Any Other Obligations and Liabilities of the Contractor Total to Tender Summary
Tender Summary
Item | Description | Sum (Euro)
1.0 | Preliminaries
2.0 | Site Clearance
3.0 | Fencing
4.0 | Safety Barriers and Pedestrian Guardrails
5.0 | Drainage and Service Ducts
6.0 | Earthworks
7.0 | Pavement
8.0 | Kerbs, Footways and Paved Areas
9.0 | Traffic Signs
10.0 | Roadmarking
11.0 | Lighting and Electrical
12.0 | Landscaping and Environmental
13.0 | Structures
14.0 | Accommodation Works
15.0 | Works (Including Main Works) for Statutory Authorities, Public and Private Utilities Companies and Organisations, Service Providers and Other Companies
16.0 | Any Other Obligations and Liabilities of the Contractor
Total Excluding Value Added Tax
Add Value Added Tax (Insert Percentage)
Total Including Value Added Tax
Notes - | Instructions to Tenderers should state that prices inserted must be representative of the resources required to carry out the works covered by the item.
- | Items to be amended/ inserted to suit project specifics particularly in relation to parts 13 and 15.
- | Additional Items to be included for unique project elements such as tunnels or signature structures

## Appendix A10 Budget Tracking
Estimate Tracking Sheet
PROJECT TITLE |  |  |  |  | DATE OF CURRENT ESTIMATE
CURRENT PHASE |  |  |  |  | BASE DATE FOR RATES
PROJECT MANAGER |  |  |  |  | ESTIMATOR (CURRENT ESTIMATE)
Phase | Date of Base Costs/ Estimate was Adjusted | Base Cost €m | Project Specific Risk Contingency €m | Total A+B | TII Total Adjustments €m | Estimate €m |  | Brief comment on key changes
|  | A | B |  |  | TC | FWC/OCE/TSB
1 | Indicative Range of Costs
not applicable
not applicable
not applicable
2 | Option Comparison Estimate (Preferred Option)
not applicable
not applicable
not applicable
3 | TC 1 and TSB, Minor Project Estimate (Target Cost 1)
4 | TC 2 and TSB, Review Minor Project Estimate (Target Cost 1)
5 | UTC 2 and TSB, Minor Project Estimate (Target Cost 2)
5 | TC 3 and TSB, Minor Project Estimate (Target Cost 3)
6/7 | Final Outturn Projection and TSB
Note : | Refer to estimate sheets for detail on programme, inflation and programme risk provisions.

## Appendix A11 Claims Compens
TYPICAL CLAIMS / COMPENSATION EVENTS REGISTER
Project Name : |  |  |  | TII Project Ref. Number : | [11 empty] | Register Prepared by : | [6 empty] | Date of Last Update : | [5 empty] | Register Updated by :
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39
Claim Reference | Date of Receipt of Notice | Brief Description of Claim / Reason for seeking adjustment to Contract Sum or Schedule | Impacted Works Element (as claimed by Contractor) | Schedule K Event Reference | [5 empty] | ER Option under Cl. 10.4 |  |  | Cl.10.3 Compliance - Contractor's Notice and Details | [5 empty] | Cl. 10.3.3 - Does Contractor allege that event has a Continuing Effect ? | Cumulative Cost and Time including Cl. 10.3.3 Compliance - Latest Information on Continuing Effects |  |  |  |  | Cl. 10.3.4 - Contemporary Records |  |  | Cl.10.5 Compliance - ER's Compliance and Cumulative Determination | [6 empty] | Has the Contractor Accepted ER determination? | Disputes
|  |  |  | Schedule K item number as assigned by Contractor | Is the Contractor Claiming the event is a Compensation Event, a Delay Event or Both ? | Does ER consider the item to be a Compensation Event ? | Does the Compensation Event satisfy requirements of Cl.10.1? | Does ER consider the item to be a Delay Event ? | Does the Delay Event satisfy requirements of Cl.10.1? | Submission sought by ER as per Cl. 10.4? | Did Contractor make submission as per ER requirement ? | Was the item agreed and confirmed as a Change Order under Cl. 4.4 ? | 1st 20 Day Rule - is the Notice Compliant ? | 2nd 20 Day Rule - Was the submission of details Compliant ? | Details Received (incl. Delay details under Cl. 9.3) |  |  |  |  | Monthly Updates Submitted ? | Information Provided as per Cl. 10.3.3 - Current Cumulative Status as of the above date |  |  |  | Cl. 10.3.4 - Did ER direct Contractor to keep particular records | Cl. 10.3.4 - Has the ER directed Contractor to submit any contemporary records | Cl. 10.3.4 - Has the Contractor complied with ER's direction to submit contemporary records | 20 Day Rule - Is the ER's Response Compliant ? | Cl. 10.5.1 (1) - Seek Additional Information or Revised Proposals |  | Cl. 10.5.1 (2), (3) and (4) - Results of Determination |  |  |  |  | If not, has the issue been referred to the Project Board (Cl. 13.1) or Conciliation (Cl. 13.2) | Has the dispute been referred to Adjudication under the CCA 2013 ? | Current Status of Dispute Resolution
[15 empty] | Facts | Cost | Time |  |  |  | Facts | Cost | Time | [5 empty] | Contractor submission - Received within 10 Days ? | ER Response within 10 Days ? | What action did ER take under Cl. 10.5.1 | Cost & Time (if ER action is item (2) or (3) of Cl 10.5.1)
[6 empty] | Insert Schedule K number if Y | Y / N | Insert Schedule K number if Y | Y / N | Y / N | Y / N | Y / N | Y / N | Y / N | Y / N | Amount € | Days - Programme Contingency | Days - EOT | Y / N | Y / N | Y / N | Amount € | Days - Programme Contingency | Days - EOT | Y / N | Y / N | Y / N | Y / N | Y / N | Y / N | Enter (2), (3) or (4) | Amount € | Days - Programme Contingency | Days - EOT | Y / N | Y (Insert Clause Ref) / N | Y / N
Cumulative Totals | [21 empty] | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0
It is intended that all Claims (including for example items which are Compensation Items, Delay Items or both) raised by the Contractor shall be recorded in this register.
Users are encouraged to contact the Project Manager with any feedback on working with the typical register and any recommendations on how it may be improved.
Figures above to exclude VAT unless otherwise stated.
Please see the following notes in relation to the completion of individual columns :
| 5 | If no item number identified by the Contractor, ER to leave blank.
| 6 | ER to enter either 'CE', 'Delay' or 'Both'
| 7 | If 'Yes', insert Schedule K item number - otherwise leave blank.
| 12 | If 'No', ER to decide on course of action - chase Contractor for details or either cancel or issue proposed instruction
| 13 | If 'Yes', skip 11 to 13 and insert agreed amounts in columns 14 to 16, 20 to 22 and 30 to 32
| 17 & 23 | It is anticipated that the Contractor will submit details of all costs (i.e. direct and delay costs)
| 21 to 25 | These Columns shall contain details of the cumulative figures for cost and time. Where there is no Continuing Effect, the cumulative figures shall be the same as those in Columns 14 to 16
| 33 to 35 | The ER's determination shall be the Cumulative determination
| 33 | The ER's determination shall similarly include for all costs.
| 36 | If 'No', Columns 37 and 38 must be completed

## Appendix B1a Risk, Qual
Sample Project Risk Register - Qualitative Analysis
State Project Title; Status of Register; Date of last Update of Register; Details of party responsible for the Register
RISK IDENTIFICATION | [6 empty] | RISK ASSESSMENT |  |  |  |  | RISK MANAGEMENT |  |  | FEED BACK |  | Murdo Notes
No | Risks | Categorisation | Project (P) or Programme Risk (TII) | Contract Risk Allocation | Applicable Cost Heading | Timing of Risk - Applicable Phase | Probability - Low/ Medium/ High | Programme Impact - Low/ Medium/ High | Financial Impact - Low/ Medium/ High | Overall Financial Impact - Low/ Medium/ High | Workshop Risk Assessment Notes | Risk Management Plan | Implementation Status | Risk Owner | Did this Risk Occur ? Y / N | If yes, what were the consequences in cost & time? | Background info, allowances incl in estimate & Risk Assessment Notes | Applicable Project Cost Estimate Heading | Timing of Risk - Applicable Phase
| Roadworks | R
| Geotechnics | G | [15 empty] | MCC | Construction
| Structures | S | [15 empty] | MCC | Construction
| Technology | T | [15 empty] | MCC | Pre Construction
| Environment (incl Archaeology) | E | [15 empty] | MCC | Pre Construction
| 3rd Parties | TP | [15 empty] | MCC | Construction
| Land & Property (incl Compensation) | L | [14 empty] | Possible impact on contractors method of working | ARCH | Construction
| Resources/Market | RM | [15 empty] | MCC | Construction
| Design Stage Programme/Procurement | P
| Buildability & Construction Programme | B
| Finance & Estimating | F | [14 empty] | Utilities Risk item | Adv
| Miscellaneous/Other-General | M | [15 empty] | MCC | Pre-Construction
[18 empty] | MCC | Construction
| Notes : | This register is not intended for use by the ER site team at the Construction phase. | [15 empty] | MCC | Construction
Risks under each head above to be identified and inserted on a project specific basis.
|  | All risks shall be numbered upon initial insertion and any subsequent risks identified for insertion shall not change the initial numbering. | [15 empty] | L&P | Pre-CPO
|  | All risks to be identified however risks classified as Programme Risk (TII Risk) which includes Strategic and Exceptional Project Specific Risk are NOT to be included in the QRA outputs. | [15 empty] | MCC | Pre-Construction
When revising the register, no risks shall be deleted - impacts shall be adjusted to reflect current information and reduced to zero when appropriate.
[18 empty] | L&P | Construction
[18 empty] | MCC | Construction
[18 empty] | MCC | Construction
[17 empty] | Likelihood of continued high demand for steel and oil based products | MCC | Construction
[18 empty] | MCC | Pre-Construction
[18 empty] | MCC | Pre-Construction
[17 empty] | Additional reports / clarifications / assurances required from tenderer. Possible expert legal advice required on excluding or accepting lowest tender. | MCC | Pre-Construction
[18 empty] | MCC | Construction
[17 empty] | Costings of temporary diversions/ lane closures - difficult to estimate at this stage. | MCC | Construction
[18 empty] | MCC | Construction
[18 empty] | MCC | Construction
[18 empty] | MCC | Construction
[18 empty] | MCC | Construction
[18 empty] | MCC | Construction
[18 empty] | MCC | Construction
[18 empty] | MCC | Pre-Construction
[18 empty] | MCC | Pre-Construction
[18 empty] | MCC | Pre & Construction
[18 empty] | MCC | Pre & Construction
[18 empty] | MCC | Pre & Construction
[18 empty] | MCC | Construction
[18 empty] | MCC | Construction
[17 empty] | Risk of disputes arising from Claims and subsequent referral to conciliation / arbitration | MCC | Construction
[17 empty] | risk that discrepancies could be exploited by Contractor and lead to claims | MCC | Pre-Construction
[18 empty] | MCC | Construction

## Appendix B1b Risk, Quant
Sample Project Risk Register - Quantitative Analysis
State Project Title; Status of Register; Date of last Update of Register; Details of party responsible for the Register
RISK IDENTIFICATION | [6 empty] | RISK ASSESSMENT | [5 empty] | RISK MANAGEMENT |  |  | FEED BACK |  | RISK QUANTIFICATION |  |  |  |  | APPROX QUANTIFICATION OUTPUT |  |  | Murdo Notes
No | Risks | Categorisation | Project (P) or Programme Risk (TII) | Contract Risk Allocation | Applicable Cost Heading | Timing of Risk - Applicable Phase | Probability Impact | Cost Impact | Time Impact | Cost Rank (PxI) | Time Rank (PxI) | Workshop Risk Assessment Notes | Risk Management Plan | Implementation Status | Risk Owner | Did this Risk Occur ? Y / N | If yes, what were the consequences in cost & time? | Correlation | Probability (P) | Min (€) | Most Likely (€) | Max (€) | P x Min (€) | P x Most Likely (€) | P x Max (€) | Background info, allowances incl in estimate & Risk Assessment Notes | Applicable Project Cost Estimate Heading | Timing of Risk - Applicable Phase
| Roadworks | R
| Geotechnics | G | [24 empty] | MCC | Construction
| Structures | S | [24 empty] | MCC | Construction
| Technology | T | [24 empty] | MCC | Pre Construction
| Environment (incl Archaeology) | E | [24 empty] | MCC | Pre Construction
| 3rd Parties | TP | [24 empty] | MCC | Construction
| Land & Property (incl Compensation) | L | [23 empty] | Possible impact on contractors method of working | ARCH | Construction
| Resources/Market | RM | [24 empty] | MCC | Construction
| Design Stage Programme/Procurement | P
| Buildability & Construction Programme | B
| Finance & Estimating | F | [23 empty] | Utilities Risk item | Adv
| Miscellaneous/Other-General | M | [24 empty] | MCC | Pre-Construction
[21 empty] | Totals |  | 0 | 0 | 0 |  | MCC | Construction
| Notes : | Figures are exclusive of VAT - to be added for final Quantitative Analysis Report. | [24 empty] | MCC | Construction
|  | This register is not intended for use by the ER site team at the Construction phase. | [17 empty] | Split | MCC | [5 empty] | MCC | Construction
|  | Risks under each head above to be identified and inserted on a project specific basis. | [18 empty] | Arch
|  | All risks shall be numbered upon initial insertion and any subsequent risks identified for insertion shall not change the initial numbering. | [18 empty] | L&P | [5 empty] | L&P | Pre-CPO
|  | All risks to be identified however risks classified as Programme Risk (TII Risk) which includes Strategic and Exceptional Project Specific Risk are NOT to be included in the QRA outputs. | [18 empty] | P&D | [5 empty] | MCC | Pre-Construction
|  | All impacts included for in the Project Risk Register shall be at rates current at the date of the preparation of the register and shall NOT include for inflation. | [18 empty] | Supervision
|  | When revising the register, no risks shall be deleted - impacts shall be adjusted to reflect current information and reduced to zero when appropriate. | [18 empty] | Enabling
[21 empty] | Diff |  | #REF! | #REF! | #REF!
[27 empty] | L&P | Construction
[27 empty] | MCC | Construction
[27 empty] | MCC | Construction
[26 empty] | Likelihood of continued high demand for steel and oil based products | MCC | Construction
[27 empty] | MCC | Pre-Construction
[27 empty] | MCC | Pre-Construction
[26 empty] | Additional reports / clarifications / assurances required from tenderer. Possible expert legal advice required on excluding or accepting lowest tender. | MCC | Pre-Construction
[27 empty] | MCC | Construction
[26 empty] | Costings of temporary diversions/ lane closures - difficult to estimate at this stage. | MCC | Construction
[27 empty] | MCC | Construction
[27 empty] | MCC | Construction
[27 empty] | MCC | Construction
[27 empty] | MCC | Construction
[27 empty] | MCC | Construction
[27 empty] | MCC | Construction
[27 empty] | MCC | Pre-Construction
[27 empty] | MCC | Pre-Construction
[27 empty] | MCC | Pre & Construction
[27 empty] | MCC | Pre & Construction
[27 empty] | MCC | Pre & Construction
[27 empty] | MCC | Construction
[27 empty] | MCC | Construction
[26 empty] | Risk of disputes arising from Claims and subsequent referral to conciliation / arbitration | MCC | Construction
[26 empty] | risk that discrepancies could be exploited by Contractor and lead to claims | MCC | Pre-Construction
[27 empty] | MCC | Construction

## Appendix B2 Risk Workshop Gu
Risk Workshop - Stages, Typical Coverage and Responsibilities
Stage | Stage Description | Indicative Timing | Activities | Coverage | Responsibility | Comment
1 | Pre-workshop | Week 1 | Briefing Meeting (if required) | Set risk study objectives and define roles | Facilitator & key project team members
|  |  | Submit base cost estimate to TII | TII review of estimate | Project Manager
|  | Week 2 | Prepare & circulate workshop handbook | Present project & workshop details | Facilitator
|  |  | Prepare for workshop | Prepare presentations | Project Manager and project team members
2 | Workshop | Week 3 - 4 | Workshop | Introductions, Overview and Outline of workshop programme | Facilitator and TII Regional Manager
|  |  |  | Technical presentations - specific areas should include Highways Design; Geotech; Structures; Archaeology; Ecology; Cost Estimate; land and Property | Team Specialists from the Employer/NRDO/Technical Advisors | Presentations typically 5 to 10 minutes max. covering key technical aspects; key assumptions and key risks
|  |  |  | Risk identification & categorising | All attendees participate - All issues, concerns and suggestions to be aired and considered | Consider whether items should be included in the base cost estimate - review cost estimate assumptions
|  |  |  | Risk impact & probability rating |  | Consequences in terms of time and cost effects - use agreed Pxl Matrix for prioritisation
|  |  |  | Devise risk response strategies |  | Must include identification of named risk owners and risk specific risk response strategies
|  |  |  | Compile Draft Risk Register | Facilitator
3 | Post Workshop | Week 4-7 | Conclude issues on workshop action list | Action list addressed and effect notified to Facilitator | All attendees with issues to action
Update Estimate
Quantify Major Risks
|  |  | Produce Draft Risk Workshop Reports | Issue draft Risk Register | Facilitator
Issue draft report
|  |  | Debrief meeting | Feedback on draft reports | All attendees with issues to action
Feedback on Updated Estimate
|  |  | Produce Final Risk Workshop Report | Final Risk Modelling | Facilitator
Final Risk Workshop Report
Final Risk Register
| Note | - | Where Risk Assessment is Qualitative, Pxl Matrix will prioritise Risk impacts by ranking as either low, medium, or high in terms of probability and impact. Following such workshops, the role of the Facilitator will not involve Risk modelling/quantitative analysis
|  | - | Value Opportunities if identified during the workshop shall be considered and recorded
|  | - | Following the completion of the workshop process as outlined above, the Project Manager shall be responsible for ensuring that the risk register is maintained and updated regularly and that all risk response strategies are implemented and monitored to ensure their effectiveness
|  | - | Risk Identification can be carried out by a selection of methods including brainstorming; reviewing assumptions; using checklists or historical registers from other projects and reviewing contract conditions and risk transfer

## Appendix B3 Construction Con
CONSTRUCTION CONTRACT RISK REGISTER
N100 - ANY CONTRACT |  |  |  |  | Current At : |  | 01/01/2021 |  | Previously Updated : |  | 2020-12-01 | Maintained by : |  |  | Position :
RISK IDENTIFICATION |  |  | Delay |  |  | RISK QUANTIFICATION |  |  |  | APPROX QUANTIFICATION OUTPUT |  |  | Risk Management
No | Risks | Cat | Prog Activity Reference | Activity Delay (Days) | Critical Path Delay (Days) | Prob (P) | Min (€) | Most Likely (€) | Max (€) | P x Min (€) | P x Most Likely (€) | P x Max (€) | Person Responsible for Managing the Risk | Claim or CE Item (Y/N) | Risk Management Plan | Implementation Status & Feedback (Did it Occur ? If Yes - Note Cost and Time Impacts)
| Roadworks | R
| Geotechnics | G
| Structures | S
| Technology | T
| Environment | E
| 3rd Parties | TP
| Resources/Market | RM
| Buildability & Construction Programme | B
| Finance | F
| Other-General | M
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Average = | 0
Notes :
| General | Risk provisions above relate solely to the Main Construction Contract
All figures above are in Euro.
All figures above are exclusive of VAT
Tha above risks MUST NOT include any provision for TII Risks - please consult with the TII Senior Engineering Inspector if clarification is required in this regard.
Claim or CE Item - refers to items that are included on either the claims or compensation events registers.
Refer to Cost Management Manual for Risk Categories
| Risk Quantification | Probabilities and min/most likely/max values must be manually inserted above
These values should be reviewed regularly and amended accordingly during the course of the construction phase
When quantifying risk items, it is recommended that time related delay costs are not included in the provision for each item.
Time related delay cost should be included under one item to be added to the risk register if the possibility of such cost occurring is identified

## Appendix B4 Project Risk Regist
Area |  |  | Conducted by |  |  |  | Date of assessment
Scheduled review date |  |  | Activity
Comments |  |  |  |  | Likelhood1 |  |  |  | Severity2
[5 empty] | 1 | Improbable |  |  | 1 | Minor Injury
[5 empty] | 2 | Occasional |  |  | 2 | Time off work
[5 empty] | 3 | Frequent |  |  | 3 | Fatality
Liklihood x Severity = Risk Factor3 ..............
Risk | Description | Mitigation / management |  | Existing control measures | Risk Assessment (after control)
[5 empty] | Likelihood1 |  |  | Severity2 |  |  | Risk Factor3
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0